## Sheet2
In scope
Basic integration testing was done covering the below modules.
Title | Description
Functional Testing | Pre-registration 1.1.3 (Dynamic UI & APIs) Registration Client (Dynamic UI, functionality and DB upgrade from 1.1.3 to 1.1.4) Kernel (APIs) Registration Processor ID Authentication (APIs) Partner Management (APIs) ID Repository (APIs) Resident Services (APIs) Admin (UI & APIs)
Configuration Testing | Testing was done both with single language and 2 languages
Version Tested | Pre reg - 1.1.3 Other modules - 1.1.4
Types of testing | Smoke Functional Integration Regression Security
Browser | Pre-Registration and Admin UI (Tested with the latest version of Chrome browser)
OS Support | Registration Client on Windows 10, MOSIP server components run as micro-services encapsulated as docker images
Not in scope
Functional | Real biometric testing
All possible notifications to be tested
Non-Functional Testing | Performance Testing Reliability and Disaster recovery Testing
HSM | Testing was done using SoftHSM
Browser Support | Testing for Pre-registration and Admin UI was done using Chrome (latest version)
Test Execution Metrics
Module | Testcases | Executed Tests | Pass | Fail | Pass% | Fail%
Pre Registration | 44 | 44 | 44 | 44 | 100% | 0%
Resident Services | 46 | 46 | 44 | 2 | 95.6% | 4.4%
Admin Services | 182 | 182 | 172 | 10 | 94.5% | 5.5%
Authentication | 55 | 55 | 53 | 2 | 96.3% | 3.7%
Partner Management | 52 | 52 | 50 | 2 | 96.1% | 3.9%
Registration | 29 | 29 | 27 | 2 | 93.1% | 6.9%
Known Issues
Bug ID | Summary | Module
MOSIP-11872 | UIN generation notification email has $name_eng | Registration
MOSIP-11842 | User role is not getting downgraded in regclient | Registration
MOSIP-11709 | [Doc] Credential issuance status is not moving from issued to printing - Restart WebSub pod | Credential Issuance