## 1.1.5.5 - Verificaton Summary
Scenario(s) verification |  |  |  | Bug(s) verification |  |  |  | Known/Pending Issues (After triage with Rounak)
Module | Scenarios | Status | Notes | Module | JIRA # | Status | Notes | Module | Issue ID | Status | Notes
Admin | Data setup (Master data, Machine (TPM Utility), center and operator mapping) | Pass |  | Reg Proc ( 1.1.5.4) | PSA-83 | Done |  | Reg proc | MOSIP-20901 |  | Documentation, will go in 1.1.5.6
Registration Client (1.1.4) | Initial launch - Login (PWD), Different user in the same machine, Logout, Reset Password,Forgot username | Pass |  |  | MOSIP-15712 | Closed |  |  | MOSIP-20943 |  | will go in 1.1.5.6
| First user Registration (Default User) | Pass |  |  | MOSIP-16638 | Closed |  |  | MOSIP-21093 | Closed | It will get fix in 1.1.5.6 ?
| Remove Default role- Operator On boarding | Pass |  |  | MOSIP-14191 | Closed
| User Roles - Default, Reg_Supervisor and Reg_Officer | Pass | MOSIP-20678 - will not fix in 1.1.4 |  | MOSIP-17290 | Closed
| Registration flow - Demogarphics, Document Upload with Ref Numbers, Biometrics, Preview and Acknoledgement. | Pass |  |  | MOSIP-14704 | Done
| Registrations Flows: Registration Type: Document based and Introducer based New: Adult,AdultExceptionLeftEye, NewAdultExceptionFP, ChildInfant, Child ExceptionEyeParent Update: Adult demo, Adult Bio, Adult Bio Exception, AdultDemoBioDoc, UpdateAdultDocs. | Pass |  |  | MOSIP-12276 | Done |  | IDA | MOSIP-20891 | Pending Dev | will go in 1.1.5.6
| With PRID: Based on age - Child and Adult. Based on PRID status Booked, incomplete, Pending, Cancelled & Expired and only with mandatory fields, with mandatory & optional fields. | Pass |  |  | MOSIP-20566 | Closed
| Lost registartion flow. | Pass |  |  | MOSIP-20434 | Closed |  |  | MOSIP-15842 | Pending Dev
| With exceptions: Adult exception Iris/FP (exception biometrics image), Infant exception -Parent Iris/FP, | Pass |  |  | MOSIP-20611 | Closed
| Update Registartion flow - Adult: Demo & Biometrics, | Pass |  |  | MOSIP-17860 | Closed
| update Child packet | Pass |  |  | MOSIP-20634 | Closed |  |  | MOSIP-20847 |  | will go in 1.1.5.6
| EoD (Pending Approval/Rajected and DashBoard) | Pass |  |  | MOSIP-20248 | Closed |  |  | MOSIP-20856 |  | will go in 1.1.5.6
| Application Upload | Pass |  |  | MOSIP-20796 | Closed
| packets export/Save to Device in online/offline mode. | Pass |  |  | MOSIP-17363 | Closed
| Synchronize Data | Pass |  |  | MOSIP-15978 | Done
| Download Pre Registration Data | Pass |  |  | MOSIP-20748 | Closed
| Operator login with FP, Iris and Face (Login, Packet Auth, Reviewer Auth, EoD auth). | Done | Biometric authentication is not supported in 1.1.4 version of regclient. |  | MOSIP-20436 | Closed
| Upgrading Reg.Client from 1.1.4 to 1.1.5.5 | Pass |  |  | MOSIP-18534 | Done
Reg Proc | Packet Receiver stage to Finalization stages | Pass |  |  | MOSIP-20905 | Closed
| UIN generation for Supervisor Approved/Rejected Packets | Pass |  |  | MOSIP-20854 | Closed |  | Verification Scope
| Email Notification based on prefered language | Pass |  |  | MOSIP-20867 | Closed |  | Dashboard | https://mosip.atlassian.net/jira/dashboards/10361?maximized=11351
IDA using APIs | Demographic authentication of Infant/adult UIN | Pass |  |  | MOSIP-20543 | Closed |  | Confluence Page | https://mosip.atlassian.net/wiki/spaces/SUP/pages/828801025/1.1.5.5
| demo/bio authentication using VID | Pass |  |  | MOSIP-20837 | Done
| Biometric authentication of adult UIN | Pass |  |  | MOSIP-20978 | Closed
| Authentication using OTP | Pass |  |  | MOSIP-20635 | Closed
| Ekyc authentication | Pass |  |  | MOSIP-21070 | Closed
| Email Notifications | Pass |  | Reg Client (1.1.5.5) | MOSIP-20868 | Closed
| Authlock/unlock from resident | Pass |  |  | MOSIP-20768 | Closed
[5 empty] | MOSIP-20824 | Closed
Resident | Request for otp using infant/adult UIN | Pass |  |  | MOSIP-20559 | Closed
| Generate VID using infant/adult UIN | Pass |  |  | MOSIP-15873 | Closed
| Revoke VID | Pass |  |  | MOSIP-15871 | Closed
| Request for credential from UIn/VID | Pass |  |  | MOSIP-15909 | Closed
| Download card for infant/adult UIN | Pass |  |  | MOSIP-16356 | Closed
| Update Infant/adult UIN | Pass |  |  | MOR-113 | Closed
| Lock/unlock UIN | Pass |  |  | MOR-134 | Closed
| Auth history | Pass |  |  | MOSIP-20440 | Closed
PMS | Create policy group and polices | Pass |  |  | MOSIP-15910 | Closed
| Self register for partner | Pass |  |  | MOSIP-20309 | Closed | Tested in qa-upgrade
| Upload certificates and generate API key | Pass |  |  | MOSIP-19227 | Closed
| Misp partner registration and MISP license key generation | Pass |  |  | MOSIP-18703 | Closed
Registration Client (1.1.5.5) | Initial launch - Login (PWD), Different user in the same machine, Logout | Pass |  |  | MOSIP-20678 | Closed
| First user Registration (Default User) | Pass |  |  | MOSIP-20825 | Closed
| Remove Default role- Operator On boarding | Pass |  |  | MOSIP-20864 | Closed | working in 1.1.5.5 version. Hence, closing this defect.
| User Roles - Default, Reg_Supervisor and Reg_Officer | Pass |  |  | MOSIP-20869 | Closed | We are not fixing this in 1,1,5.5 version.
| Registration flow - Demogarphics, Document Upload with Ref Numbers, Biometrics, Preview and Acknoledgement. | Pass |  |  | MOSIP-20870 | Closed | We are not fixing this in 1,1,5.5 version.
| Registrations Flows: Registration Type: Document based and Introducer based New: Adult,AdultExceptionLeftEye, NewAdultExceptionFP, ChildInfant, Child ExceptionEyeParent | Pass |  |  | MOSIP-20548 | Closed
| With PRID: Based on age - Child and Adult. Based on PRID status Booked, incomplete, Pending, Cancelled & Expired and only with mandatory fields, with mandatory & optional fields. | Pass |  |  | MOSIP-20844 | Closed | This is the expected behaviour with any version lower than 1.2.0, hence we will not fix this.
| Lost registartion flow. | Pass |  |  | MOSIP-20871 | Closed
| With exceptions: Adult exception Iris/FP (exception biometrics image), Infant exception -Parent Iris/FP, | Pass |  |  | MOSIP-20855 | Closed | Duplicate
| Update: Adult demo, Adult Bio, Adult Bio Exception, AdultDemoBioDoc, UpdateAdultDocs. | Pass |  |  | MOSIP-20474 | Closed
| update Child packet | Pass |  | Commons (1.1.5.5) | MOSIP-17991 | Closed
| EoD (Pending Approval/Rajected) | Pass |  |  | MOSIP-17298 | Closed | Performance issue
| Application Upload | Pass |  |  | MOSIP-17565 | Closed | Performance issue
| packets export/Save to Device in online/offline mode. | Pass |  |  | MOSIP-18380 | Closed | Performance issue
| Synchronize Data | Pass |  |  | MOSIP-17980 | Closed | Performance issue
| Center Remapping | Pass |  |  | MOSIP-18878 | Closed
| Download Pre Registration Data | Pass
| Operator login with FP, Iris and Face (Login, Packet Auth, Reviewer Auth, EoD auth). | Pass |  | Admin (1.1.5.3) | MOSIP-17282 | Closed
IDA using Auth UI | Demographic authentication of Infant/adult UIN | Pass |  |  | MOSIP-17735 | Done
| Bio face authentication with adult UIN | Pass
| Bio iris/finger authentication with adult UIN | Pass |  | IDA (1.1.5.5) | MOSIP-16654 | Done
| demo authentication using VID | Pass |  |  | MOSIP-17106 | Done
| bio face authentication using VID | Pass |  |  | MOSIP-17523 | Closed
| bio iris/finger authentication using VID | Pass |  |  | MOSIP-16870 | Done
| Authentication using OTP | Pass |  |  | MOSIP-16784 | Closed
| Ekyc authentication for demo | Pass |  |  | MOSIP-17300 | Closed
| Ekyc authentication for Bio face | Pass |  |  | MOSIP-17302 | Closed
| Ekyc authentication for Bio iris/finger | Pass |  |  | MOSIP-18523 | Closed | Performance issue
| Email Notifications | Pass |  |  | MOSIP-20390 | Closed
| Authlock/unlock from resident | Pass |  |  | MOSIP-20766 | Closed
[5 empty] | MOSIP-20240 | Closed
[5 empty] | MOSIP-19917 | Closed
[5 empty] | MOSIP-20764 | Closed
[5 empty] | MOSIP-20289 | Closed
[5 empty] | MOSIP-20849 | Closed
[5 empty] | MOSIP-20765 | Closed
[5 empty] | MOSIP-20895 | Closed
[5 empty] | MOSIP-21059 | Closed
|  |  |  | Resident Services | MOSIP-20638 | Closed
[5 empty] | MOSIP-19916 | Closed
[5 empty] | MOSIP-20827 | Closed
[5 empty] | MOSIP-20892 | Closed
[5 empty] | MOSIP-20832 | Closed