## Summary
Compliance Tool Kit (CTK)v1.1.0 - Verification Summary
Windows - SBI Testing
Test(s) Metrics | With Mock | [5 empty] | With Device | [5 empty] | Mock Details: - MOSIP mock SBI 1.2.1-snapshot Note: Windows CTK with real devices are not in scope
| Auth |  |  | Reg |  |  | Auth |  |  | Reg
| FP | IRIS | Face | FP | IRIS | Face | FP | IRIS | Face | FP | IRIS | Face
Total | 19 | 21 | 15 | 35 | 21 | 20 | 19 | 21 | 15 | 35 | 21 | 20
Passed | 19 | 21 | 15 | 35 | 21 | 20 | 0 | 0 | 0 | 0 | 0 | 0
Failed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18 | 13 | 30 | 18 | 17
Test Rate (%) | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
Pass Rate (%) | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
Android - SBI Testing
Test(s) Metrics | With Mock | [5 empty] | With Device | [5 empty] | Mock Details: - MOSIP Android mock SBI Device Details: - Registration: NPrime Face SBI
| Auth |  |  | Reg |  |  | Auth |  |  | Reg
| FP | IRIS | Face | FP | IRIS | Face | FP | IRIS | Face | FP | IRIS | Face
Total | 19 | 21 | 15 | 29 | 18 | 17 | 19 | 21 | 15 | 29 | 18 | 17
Passed | 19 | 21 | 15 | 29 | 18 | 17 | 0 | 0 | 0 | 0 | 0 | 3
Failed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21 | 15 | 29 | 18 | 0
Test Rate (%) | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 100
Pass Rate (%) | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 17.6471
Windows - SDK Testing
Test(s) Metrics | With Windows-SDK | [11 empty] | Mock '''Windows-SDK''' Details: - MOSIP mock SDK 1.2.1-SNAPSHOT' 'Windows-SDK' Note: Segmentation out of scope Real windows SDK testing is not in scope
| Mock | Tech5 | NPrime
Total | 76 | 76 | 76
Passed | 65 | 0 | 0
Failed | 0 | 0 | 0
Pending | 0 | 0 | 0
N/A | 11 | 76 | 76
Test Rate (%) | 85.5263 | 0 | 0
Pass Rate (%) | 85.5263 | 0 | 0

## Windows-SBI
S.No | Test Id | Auth-Iris | Auth-Face | Auth-FP | Reg Iris | Reg Face | Reg FP | Test Name | Test Description | Validator | Type | STATUS | Dev Comments | Results (Reg Iris) | Results (Reg Face) | Results (Reg FP) | Results (Auth FP) | Results (Auth IRIS) | Results (Auth Face) | Results (Mock - Reg Iris) | Results (Mock - Reg Face) | Results (Mock - Reg FP) | Results (Mock - Auth-FP) | Results (Mock - Auth-Face) | Results (Mock - Auth_IRIS)
1 | SBI1000 | Yes | Yes | Yes | Yes | Yes | Yes | Discover device | This testcase will perform device discovery for the selected device. | SchemaValidator SignatureValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
2 | SBI1001 | Yes | Yes | Yes | Yes | Yes | Yes | Device Info | This testcase will validate the device info for the selected device including trust validation. | SchemaValidator SignatureValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
3 | SBI1002 | No | No | No | No | No | Yes | Registration capture - Left Slab | This testcase is to check if Registration Capture for Left Slap from the device is valid or not. | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
4 | SBI1003 | No | No | No | No | No | Yes | Registration capture - Left Slab - One Exception | 1. This testcase is to check if Registration Capture for Left Slap from the device is valid or not.<br> 2. Please place your left slap <b>except left ring finger</b> on the device. | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
5 | SBI1004 | No | No | No | No | No | Yes | Registration capture - Right Slab | Valid Registration capture Request for Slap scanner type | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
6 | SBI1005 | No | No | No | No | No | Yes | Registration capture - Right Slab - Two Exception | Valid Registration capture Request for slap device type with right slap except right ring finger and right little finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
7 | SBI1006 | No | No | No | No | No | Yes | Registration capture - Two Thumbs | Valid Registration capture Request for Slap scanner type | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
8 | SBI1007 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - One Exception | Valid Registration capture Request for slap device type with two thumbs except left thumb finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
9 | SBI1008 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Both Exception | Valid Registration capture Request for slap device type with two thumbs except right thumb finger and left thumb finger | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
10 | SBI1009 | No | No | No | Yes | No | No | Registration capture - Double Iris | Valid Registration capture Request | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
11 | SBI1010 | No | No | No | Yes | No | No | Registration capture - Double Iris - One Exception | Valid Registration capture Request for Double iris device type except left iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
12 | SBI1011 | No | No | No | Yes | No | No | Registration capture - Double Iris - Both Exception | Valid Registration capture Request for Double iris device type except left iris and right iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
13 | SBI1012 | No | No | No | No | Yes | No | Registration capture - Face | Valid Registration capture Request only for Face | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
14 | SBI1013 | No | No | No | No | Yes | No | Registration capture - Exception Photo | Valid Registration capture Request for Face device type exception value left little finger or any will give Exception photo | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
15 | SBI1014 | No | Yes | No | No | No | No | Auth capture - Face | Valid Auth capture Request only for Face | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
16 | SBI1015 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris | Valid Auth capture Request for Unknown iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
17 | SBI1016 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris | Valid Auth capture Request for Left iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
18 | SBI1017 | Yes | No | No | No | No | No | Auth capture - Single Iris - Right Iris | Valid Auth capture Request for Right iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
19 | SBI1018 | No | No | Yes | No | No | No | Auth capture - Unknown Finger | Valid Auth capture Request for Unknown Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
20 | SBI1019 | No | No | Yes | No | No | No | Auth capture -Two Unknown Finger | Valid Auth capture Request for Two Unknown Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
21 | SBI1020 | No | No | Yes | No | No | No | Auth capture - LeftIndex Finger | Valid Auth capture Request for LeftIndex Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
22 | SBI1021 | No | No | Yes | No | No | No | Auth capture - Two Finger | Valid Auth capture Request for Two Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
23 | SBI1022 | No | No | No | No | No | Yes | Registration capture - Key Rotation - Left Slap | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
24 | SBI1023 | Yes | No | No | No | No | No | Auth capture -Key Rotation - Single Iris - Left Iris | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
25 | SBI1024 | No | No | Yes | No | No | No | Auth capture - Key Rotation - LeftIndex Finger | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
26 | SBI1025 | No | Yes | No | No | No | No | Auth capture - Face - Key Rotation | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
27 | SBI1026 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Ready | Test to validate Device Info interface for a device that is in Ready state | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
28 | SBI1027 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Busy | Test to validate if the device is in Busy state | SchemaValidator | Device Status | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
29 | SBI1028 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Not Ready | Test to validate if the device is in Not Ready state | SchemaValidator | Device Status | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
30 | SBI1029 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Not Registered | Test to validate if the device is in Not Registered state | SchemaValidator | Device Status | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass
31 | SBI1030 | No | No | Yes | No | No | No | Auth capture - Fingerprint - Bio Count Mismatch | Test to validate bio count mismatch for auth fingerprint device | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
32 | SBI1031 | Yes | No | No | No | No | No | Auth capture - Iris - Bio Count Mismatch | Test to validate bio count mismatch for auth iris device | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
33 | SBI1032 | No | Yes | No | No | No | No | Auth capture - Face - Bio Count Mismatch | Test to validate bio count mismatch for face | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
34 | SBI1033 | No | No | No | No | No | Yes | Registration capture - Left Slap - Bio Count Mismatch | Test to validate bio count mismatch for registration left slap | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
35 | SBI1034 | No | No | No | No | No | Yes | Registration capture - Right Slap - Bio Count Mismatch | Test to validate bio count mismatch for registration right slap | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
36 | SBI1035 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Bio Count Mismatch | Test to validate bio count mismatch for registration thumbs | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
37 | SBI1036 | No | No | No | Yes | No | No | Registration capture - Left iris - Bio Count Mismatch | Test to validate bio count mismatch for registration left iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
38 | SBI1037 | No | No | No | Yes | No | No | Registration capture - Right Iris - Bio Count Mismatch | Test to validate bio count mismatch for registration right iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
39 | SBI1038 | No | No | No | Yes | No | No | Registration capture - Both Iris - Bio Count Mismatch | Test to validate bio count mismatch for registration both iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
40 | SBI1039 | No | No | No | No | Yes | No | Registration capture - Face - Bio Count Mismatch | Test to validate bio count mismatch for registration face | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
41 | SBI1040 | No | No | No | No | Yes | No | Registration capture - Face - Timeout | Test to validate face timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
42 | SBI1042 | No | No | No | No | No | Yes | Registration capture - Left Slap - Timeout | Test to validate left slap timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
43 | SBI1043 | No | No | No | No | No | Yes | Registration capture - Right Slap - Timeout | Test to validate right slap timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
44 | SBI1044 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Timeout | Test to validate thumb timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
45 | SBI1041 | No | No | No | Yes | No | No | Registration capture - Double Iris - Timeout | Test to validate iris timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
46 | SBI1045 | No | No | No | No | Yes | No | Registration capture - Exception Photo - Timeout | Test to validate exception photo timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
47 | SBI1051 | No | No | No | No | No | Yes | Registration capture - Left Slap - Force Capture | Force Capture validation for registration capture request for Left Slap | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
48 | SBI1052 | No | No | No | No | No | Yes | Registration capture - Right Slap - Force Capture | Force Capture validation for registration capture request for Right Slap | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
49 | SBI1053 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Force Capture | Force Capture validation for registration capture request for Two Thumbs | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 3 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
50 | SBI1050 | No | No | No | Yes | No | No | Registration capture - Double Iris - Force Capture | Force Capture validation for registration capture request for double iris | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
51 | SBI1049 | No | No | No | No | Yes | No | Registration capture - Face - Force Capture | Force Capture validation for registration capture request for face | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
52 | SBI1054 | No | No | No | No | Yes | No | Registration capture - Exception Photo - Force Capture | Force Capture validation for Face device type exception value left little finger or any will give Exception photo | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 2 new testcases. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
53 | SBI1057 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Force Capture | Force Capture validation for Auth capture Request for Unknown Finger | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
54 | SBI1056 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris - Force Capture | Force Capture validation for Auth capture Request for Unknown iris | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
55 | SBI1055 | No | Yes | No | No | No | No | Auth capture - Face - Force Capture | Force Capture validation for Auth capture Request only for Face | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
56 | SBI1048 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Timeout | Test to validate finger timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
57 | SBI1047 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris - Timeout | Test to validate iris timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
58 | SBI1046 | No | Yes | No | No | No | No | Auth capture - Face - Timeout | Test to validate face timeout | SchemaValidator TimeoutValidator | Timeout | Available | Added 1 new testcase. Available in 1.0.0-b1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
59 | SBI1058 | No | No | Yes | No | No | No | Auth capture - 10 Fingers | Test to perform Auth capture for 10 Fingers | SchemaValidator ResponseMismatchValidator SignatureValidator | ResponseMismatchValidator | Available | Available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
60 | SBI1059 | Yes | No | No | No | No | No | Auth capture - 2 Iris | Test to perform Auth capture for 2 Iris | SchemaValidator ResponseMismatchValidator SignatureValidator | ResponseMisMatchValidator | Available | Available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
61 | SBI1060 | No | No | No | No | Yes | No | Registration capture - Key Rotation - Face | Test for device key rotation | KeyRotationValidator | KeyRotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
62 | SBI1061 | No | No | No | Yes | No | No | Registration capture - Key Rotation - Double Iris | Test for device key rotation | KeyRotationValidator | KeyRotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
63 | SBI1062 | No | No | No | No | No | Yes | Registration capture - Left Slap - ISO Standard Validations | Test to validate the RCapture interface for Left Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
64 | SBI1063 | No | No | No | No | No | Yes | Registration capture - Right Slap - ISO Standard Validations | Test to validate RCapture interface for Right Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
65 | SBI1064 | No | No | No | Yes | No | No | Registration capture - Double Iris - ISO Standard Validations | Test to validate RCapture interface for Two Iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
66 | SBI1065 | No | No | No | No | Yes | No | Registration capture - Face - ISO Standard Validations | Test to validate RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
67 | SBI1066 | No | Yes | No | No | No | No | Auth capture - Face - ISO Standard Validations | Test to validate Capture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
68 | SBI1067 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris - ISO Standard Validations | Test to validate Capture interface for left iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
69 | SBI1068 | Yes | No | No | No | No | No | Auth capture - Single Iris - Right Iris - ISO Standard Validations | Test to validate Capture interface for right iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
70 | SBI1069 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - ISO Standard Validations | Test to validate Capture interface for a finger | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
71 | SBI1070 | No | No | No | No | No | Yes | Streaming test with Registration capture - Left Slap | Streaming Test to validate the RCapture interface for Left Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
72 | SBI1071 | No | No | No | No | No | Yes | Streaming test with Registration capture - Right Slap | Streaming Test to validate the RCapture interface for Right Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
73 | SBI1072 | No | No | No | No | No | Yes | Streaming test with Registration capture - Two Thumbs | Streaming Test to validate the RCapture interface for Two Thumbs | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
74 | SBI1073 | No | No | No | Yes | No | No | Streaming test with Registration capture - Double Iris | Streaming Test to validate the RCapture interface for Two Iris | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
75 | SBI1074 | No | No | No | No | Yes | No | Streaming test with Registration capture - Face | Streaming Test to validate the RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
76 | SBI1075 | No | No | No | No | No | Yes | Biometrics Quality Check for Registration capture - Left Slap | Quality Check Test to validate the biometrics captured by RCapture interface for left slap fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
77 | SBI1076 | No | No | No | No | No | Yes | Biometrics Quality Check for Registration capture - Right Slap | Quality Check Test to validate the biometrics captured by RCapture interface for right slap fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A
78 | SBI1077 | No | No | No | Yes | No | No | Biometrics Quality Check for Registration capture - Double Iris | Quality Check Test to validate the biometrics captured by RCapture interface for both iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A
79 | SBI1078 | No | No | No | No | Yes | No | Biometrics Quality Check for Registration capture - Face | Quality Check Test to validate the biometrics captured by RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A
80 | SBI1079 | No | Yes | No | No | No | No | Biometrics Quality Check for Auth capture - Face | Quality Check Test to validate the biometrics captured by Capture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A
81 | SBI1080 | Yes | No | No | No | No | No | Biometrics Quality Check for Auth capture - Single Iris - Left Iris | Quality Check Test to validate the biometrics captured by Capture interface for left iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
82 | SBI1081 | Yes | No | No | No | No | No | Biometrics Quality Check for Auth capture - Single Iris - Right Iris | Quality Check Test to validate the biometrics captured by Capture interface for right iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass
83 | SBI1082 | No | No | Yes | No | No | No | Biometrics Quality Check for Auth capture - Unknown Finger | Quality Check Test to validate the biometrics captured by Capture interface for a finger | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A
84 | SBI1083 | No | No | No | No | No | Yes | Time Check for Registration capture - Left Slap | Test to validate the timestamp captured by RCapture interface for left slap fingerprints | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | Pass | N/A | N/A | N/A
85 | SBI1084 | No | No | No | No | No | Yes | Time Check for Registration capture - Right Slap | Test to validate the timestamp captured by RCapture interface for right slap fingerprints | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | Pass | N/A | N/A | N/A
86 | SBI1085 | No | No | No | Yes | No | No | Time Check for Registration capture - Double Iris | Test to validate the timestamp captured by RCapture interface for both iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | Pass | N/A | N/A | N/A | N/A | N/A
87 | SBI1086 | No | No | No | No | Yes | No | Time Check for Registration capture - Face | Test to validate the timestamp captured by RCapture interface for face | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | Pass | N/A | N/A | N/A | N/A
88 | SBI1087 | No | Yes | No | No | No | No | Time Check for Auth capture - Face | Test to validate the timestamp captured by Capture interface for face | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | N/A | N/A | Pass | N/A
89 | SBI1088 | Yes | No | No | No | No | No | Time Check for Auth capture - Single Iris - Left Iris | Test to validate the timestamp captured by Capture interface for left iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | N/A | N/A | N/A | Pass
90 | SBI1089 | Yes | No | No | No | No | No | Time Check for Auth capture - Single Iris - Right Iris | Test to validate the timestamp captured by Capture interface for right iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | N/A | N/A | N/A | Pass
91 | SBI1090 | No | No | Yes | No | No | No | Time Check for Auth capture - Unknown Finger | Test to validate the timestamp captured by Capture interface for a finger | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available | [7 empty] | N/A | N/A | N/A | Pass | N/A | N/A
92 | SBI1091 | No | Yes | No | No | No | No | Auth capture - Face - Invalid Transaction Id | Test to validate transactionId of Capture method for face | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available | [7 empty] | N/A | N/A | N/A | N/A | Pass | N/A
93 | SBI1092 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris - Invalid Transaction Id | Test to validate transactionId of Capture method for left iris | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available | [7 empty] | N/A | N/A | N/A | N/A | N/A | Pass
94 | SBI1093 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Invalid Transaction Id | Test to validate transactionId of Capture method for a finger | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available | [7 empty] | N/A | N/A | N/A | Pass | N/A | N/A
95 | SBI1094 | No | No | No | No | No | Yes | Registration capture - Left Slap - Invalid Request Json (wrong attribute name envXXX) | Test to validate invalid request json in RCapture method for Left Slap Fingerprints | SchemaValidator | Invalid Request Json | Available | [7 empty] | N/A | N/A | Pass | N/A | N/A | N/A
96 | SBI1095 | No | No | No | No | No | Yes | Registration capture - Right Slap - Invalid Request Json (wrong attribute name timeoutXXX) | Test to validate invalid request json in RCapture method for Right Slap Fingerprints | SchemaValidator | Invalid Request Json | Available | [7 empty] | N/A | N/A | Pass | N/A | N/A | N/A
97 | SBI1096 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Invalid Request Json (wrong attribute name specVersionXXX) | Test to validate invalid request json in RCapture method for Two Thumbs | SchemaValidator | Invalid Request Json | Available | [7 empty] | N/A | N/A | Pass | N/A | N/A | N/A
98 | SBI1097 | No | No | No | Yes | No | No | Registration capture - Double Iris - Invalid Request Json (wrong attribute name purposeXXX) | Test to validate invalid request json in RCapture method for Two Iris | SchemaValidator | Invalid Request Json | Available | [7 empty] | Pass | N/A | N/A | N/A | N/A | N/A
99 | SBI1098 | No | No | No | No | Yes | No | Registration capture - Face - Invalid Request Json (wrong attribute name bioXXX) | Test to validate invalid request json in RCapture method for face | SchemaValidator | Invalid Request Json | Available | [7 empty] | N/A | Pass | N/A | N/A | N/A | N/A
100 | SBI1099 | No | No | No | Yes | No | No | Registration capture - Double Iris - One Exception - Invalid Request Json (wrong attribute name countXXX) | Test to validate invalid request json in RCapture method for iris with one missing iris | SchemaValidator | Invalid Request Json | Available | [7 empty] | Pass | N/A | N/A | N/A | N/A | N/A
101 | SBI1100 | No | No | No | No | Yes | No | Registration capture - Exception Photo - Invalid Request Json (wrong attribute name deviceSubIdXXX) | Test to validate invalid request json in RCapture method for exception photo | SchemaValidator | Invalid Request Json | Available | [7 empty] | N/A | Pass | N/A | N/A | N/A | N/A

## Windows-SDK
S.No | Test Id | Test Name | Synthetic testdata possible? | Test Description | Validator | STATUS | Real SDK (Tech5) | Mock SDK | Real SDK (NPrime)
1 | SDK2000 | Init Test | N/A | Initialise Bio SDK Services | SchemaValidator | Available | N/A | Pass | N/A
2 | SDK2001 | Good face quality | Yes | 1. This testcase checks the biomterics for face to be of good quality.<br>2. Add the appropriate probe.xml | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
3 | SDK2002 | Bad face quality | Yes | Bad face quality | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
4 | SDK2003 | Invalid face data for quality check | Yes | Invalid face data for quality check | SchemaValidator QualityCheckInvalidDataValidator | Available | N/A | Pass | N/A
5 | SDK2004 | No face data for quality check | Yes | No face data for quality check | SchemaValidator QualityCheckNoDataValidator | Available | N/A | Pass | N/A
6 | SDK2005 | Bad finger quality | Yes | Bad finger quality | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
7 | SDK2006 | Good finger quality | Yes | Good finger quality | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
8 | SDK2007 | Invalid finger data for quality check | Yes | Invalid finger data for quality check | SchemaValidator QualityCheckInvalidDataValidator | Available | N/A | Pass | N/A
9 | SDK2008 | No finger data for quality check | Yes | No finger data for quality check | SchemaValidator QualityCheckNoDataValidator | Available | N/A | Pass | N/A
10 | SDK2009 | Bad iris quality | Not Available | Bad iris quality | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
11 | SDK2010 | Good iris quality | Not Available | Good iris quality | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
12 | SDK2011 | Invalid iris data for quality check | Not Available | Invalid iris data for quality check | SchemaValidator QualityCheckInvalidDataValidator | Available | N/A | Pass | N/A
13 | SDK2012 | No iris data for quality check | Yes | No iris data for quality check | SchemaValidator QualityCheckNoDataValidator | Available | N/A | Pass | N/A
14 | SDK2013 | Multi modality (face & finger) quality check success | Yes | modality quality check success | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
15 | SDK2014 | Multi modality (Face,Finger,Iris) quality check success | Not Available | modality quality check success | SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
16 | SDK2015 | Face match failure | Yes | Face match failure | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
17 | SDK2016 | Face match success | Yes | Face match success | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
18 | SDK2017 | Invalid face data for match | Yes | Invalid face data for match | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
19 | SDK2018 | No face data for match | Yes | No face data for match | SchemaValidator MatchNoDataValidator | Available | N/A | Pass | N/A
20 | SDK2019 | Face match against more than one face | Yes | Face match against more than one face | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
21 | SDK2020 | Sending finger data instead of face | Yes | Sending finger data instead of face | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
22 | SDK2021 | Finger match failure | Yes | Finger match failure | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
23 | SDK2022 | Finger match success | Yes | Finger match success | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
24 | SDK2023 | Invalid finger data for match | Yes | Invalid finger data for match | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
25 | SDK2024 | No finger data for match | Yes | No finger data for match | SchemaValidator MatchNoDataValidator | Available | N/A | Pass | N/A
26 | SDK2025 | Finger match against more than 10 fingers | Yes | Finger match against more than 10 fingers | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
27 | SDK2026 | Finger match when wrong subtype | Yes | Finger match when wrong subtype | SchemaValidator MatchValidator | Available | N/A | N/A | N/A
28 | SDK2027 | Sending face data instead of finger | Yes | Sending face data instead of finger | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
29 | SDK2028 | Iris match failure | Not Available | Iris match failure | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
30 | SDK2029 | Iris match success | Not Available | Iris match success | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
31 | SDK2030 | Invalid iris data for match | Not Available | Invalid iris data for match | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
32 | SDK2031 | No iris data for match | Yes | No iris data for match | SchemaValidator MatchNoDataValidator | Available | N/A | Pass | N/A
33 | SDK2032 | Iris match against more than 2 iris | Not Available | Iris match against more than 2 iris | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
34 | SDK2033 | Iris match when wrong subtype | Not Available | Iris match when wrong subtype | SchemaValidator MatchValidator | Available | N/A | N/A | N/A
35 | SDK2034 | Sending face data instead of iris | Yes | Sending face data instead of iris | SchemaValidator MatchInvalidDataValidator | Available | N/A | Pass | N/A
36 | SDK2035 | Multi modality (Face,Finger) match success | Yes | modality match success | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
37 | SDK2036 | Multi modality (Face,Finger,Iris) match success | Not Available | Multi modality match success | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
38 | SDK2037 | Multi modality (Face,Finger,Iris) match success - multi gallery | Not Available | Multi modality match success - multi gallery | SchemaValidator MatchValidator | Available | N/A | Pass | N/A
39 | SDK2038 | Finger Extract Template And Check Quality Success | Yes | Finger extract Template And CheckQuality Success | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
40 | SDK2039 | Face Extract Template And Check Quality Success | Yes | Face extract Template And CheckQuality Success | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
41 | SDK2040 | Iris Extract Template And Check Quality Success | Not Available | Iris extract Template And CheckQuality Success | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
42 | SDK2041 | Finger Extract Template And Check Quality Fail | Yes | Finger extract Template And CheckQuality Fail | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
43 | SDK2042 | Face Extract Template And Check Quality Fail | Yes | Face extract Template And CheckQuality Fail | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
44 | SDK2043 | Iris Extract Template And Check Quality Fail | Not Available | Iris extract Template And CheckQuality Fail | SchemaValidator ExtractTemplateValidator SchemaValidator QualityCheckValidator | Available | N/A | Pass | N/A
45 | SDK2044 | Finger extract invalid data failure | Yes | Finger extract invalid data failure | SchemaValidator ExtractTemplateInvalidDataValidator | Available | N/A | Pass | N/A
46 | SDK2045 | Face extract invalid data failure | Yes | Face extract invalid data failure | SchemaValidator ExtractTemplateInvalidDataValidator | Available | N/A | Pass | N/A
47 | SDK2046 | Iris extract invalid data failure | Not Available | Iris extract invalid data failure | SchemaValidator ExtractTemplateInvalidDataValidator | Available | N/A | Pass | N/A
48 | SDK2047 | Finger extract no input failure | Yes | Finger extract no input failure | SchemaValidator ExtractTemplateNoInputDataValidator | Available | N/A | Pass | N/A
49 | SDK2048 | Face extract no input failure | Yes | Face extract no input failure | SchemaValidator ExtractTemplateNoInputDataValidator | Available | N/A | Pass | N/A
50 | SDK2049 | Iris extract no input failure | Yes | Iris extract no input failure | SchemaValidator ExtractTemplateNoInputDataValidator | Available | N/A | Pass | N/A
51 | SDK2050 | Finger Extract Template And Match FMR Success | Yes | Finger Extract And Match FMR Success | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
52 | SDK2051 | Face Extract Template And Match FMR Success | Yes | Face Extract And Match FMR Success | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
53 | SDK2052 | Iris Extract Template And Match FMR Success | Not Available | Iris Extract And Match FMR Success | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
54 | SDK2053 | Finger Extract Template And Match FMR Fail | Yes | Finger Extract And Match FMR Fail | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
55 | SDK2054 | Face Extract Template And Match FMR Fail | Yes | Face Extract And Match FMR Fail | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
56 | SDK2055 | Iris Extract Template And Match FMR Fail | Not Available | Iris Extract And Match FMR Fail | SchemaValidator ExtractTemplateValidator SchemaValidator MatchValidator | Available | N/A | Pass | N/A
57 | SDK2056 | Finger segment good quality | Yes | Finger segment good quality | SchemaValidator SegmentValidator | Available | N/A | N/A | N/A
58 | SDK2057 | Face segment good quality | Yes | Face segment good quality | SchemaValidator SegmentValidator | Available | N/A | N/A | N/A
59 | SDK2058 | Iris segment good quality | Not Available | Iris segment good quality | SchemaValidator SegmentValidator | Available | N/A | N/A | N/A
60 | SDK2059 | Finger segment invalid data failure | Yes | Finger segment invalid data failure | SchemaValidator SegmentInvalidDataValidator | Available | N/A | N/A | N/A
61 | SDK2060 | Face segment invalid data failure | Yes | Face segment invalid data failure | SchemaValidator SegmentInvalidDataValidator | Available | N/A | N/A | N/A
62 | SDK2061 | Iris segment invalid data failure | Not Available | Iris segment invalid data failure | SchemaValidator SegmentInvalidDataValidator | Available | N/A | N/A | N/A
63 | SDK2062 | Finger segment no input failure | Yes | Finger segment no input failure | SchemaValidator SegmentNoInputDataValidator | Available | N/A | N/A | N/A
64 | SDK2063 | Face segment no input failure | Yes | Face segment no input failure | SchemaValidator SegmentNoInputDataValidator | Available | N/A | N/A | N/A
65 | SDK2064 | Iris segment no input failure | Yes | Iris segment no input failure | SchemaValidator SegmentNoInputDataValidator | Available | N/A | N/A | N/A
66 | SDK2065 | Face convert from ISO19794_5_2011 to IMAGE/JPEG | Yes | Face convert from ISO19794_5_2011 to IMAGE/JPEG | SchemaValidator ConvertDataValidator | Available | N/A | Pass | N/A
67 | SDK2066 | Face convert from ISO19794_5_2011 to IMAGE/PNG | Yes | Face convert from ISO19794_5_2011 to IMAGE/PNG | SchemaValidator ConvertDataValidator | Available | N/A | Pass | N/A
68 | SDK2067 | Face convert invalid data failure | Yes | Face convert invalid data failure | SchemaValidator ConvertInvalidDataValidator | Available | N/A | Pass | N/A
69 | SDK2068 | Face convert no input failure | Yes | Face convert no input failure | SchemaValidator ConvertNoInputDataValidator | Available | N/A | Pass | N/A
70 | SDK2069 | Finger convert from ISO19794_4_2011 to IMAGE/JPEG | Yes | Finger convert from ISO19794_4_2011 to IMAGE/JPEG | SchemaValidator ConvertDataValidator | Available | N/A | Pass | N/A
71 | SDK2070 | Finger convert from ISO19794_4_2011 to IMAGE/PNG | Yes | Finger convert from ISO19794_4_2011 to IMAGE/PNG | SchemaValidator ConvertDataValidator | Available | N/A | Pass | N/A
72 | SDK2071 | Finger convert invalid data failure | Yes | Finger convert invalid data failure | SchemaValidator ConvertInvalidDataValidator | Available | N/A | Pass | N/A
73 | SDK2072 | Finger convert no input failure | Yes | Finger convert no input failure | SchemaValidator ConvertNoInputDataValidator | Available | N/A | Pass | N/A
74 | SDK2073 | Iris convert from ISO19794_6_2011 to IMAGE/PNG | Not Available | Iris convert from ISO19794_6_2011 to IMAGE/PNG | SchemaValidator ConvertDataValidator | Available | N/A | Pass | N/A
75 | SDK2074 | Iris convert invalid data failure | Not Available | Iris convert invalid data failure | SchemaValidator ConvertInvalidDataValidator | Available | N/A | Pass | N/A
76 | SDK2075 | Iris convert no input failure | Not Available | Iris convert no input failure | SchemaValidator ConvertNoInputDataValidator | Available | N/A | Pass | N/A

## Android-SBI
. | Test Id | Auth-Iris | Auth-Face | Auth-FP | Reg Iris | Reg Face | Reg FP | Test Name | Test Description | Validator | Type | STATUS | Dev Comments | Results (Reg Iris) | Results (Reg Face) | Results (Reg FP) | Results (Auth FP) | Results (Auth IRIS) | Results (Auth Face) | Results (Mock - Reg Iris) | Results (Mock - Reg Face) | Results (Mock - Reg FP) | Results (Mock - Auth-FP) | Results (Mock - Auth-Face) | Results (Mock - Auth_IRIS) | Android
1 | SBI1000 | Yes | Yes | Yes | Yes | Yes | Yes | Discover device | This testcase will perform device discovery for the selected device. | SchemaValidator SignatureValidator |  | Available |  | N/A | Pass | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
2 | SBI1001 | Yes | Yes | Yes | Yes | Yes | Yes | Device Info | This testcase will validate the device info for the selected device including trust validation. | SchemaValidator SignatureValidator |  | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
3 | SBI1002 | No | No | No | No | No | Yes | Registration capture - Left Slab | This testcase is to check if Registration Capture for Left Slap from the device is valid or not. | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
4 | SBI1003 | No | No | No | No | No | Yes | Registration capture - Left Slab - One Exception | 1. This testcase is to check if Registration Capture for Left Slap from the device is valid or not.<br> 2. Please place your left slap <b>except left ring finger</b> on the device. | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
5 | SBI1004 | No | No | No | No | No | Yes | Registration capture - Right Slab | Valid Registration capture Request for Slap scanner type | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
6 | SBI1005 | No | No | No | No | No | Yes | Registration capture - Right Slab - Two Exception | Valid Registration capture Request for slap device type with right slap except right ring finger and right little finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
7 | SBI1006 | No | No | No | No | No | Yes | Registration capture - Two Thumbs | Valid Registration capture Request for Slap scanner type | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
8 | SBI1007 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - One Exception | Valid Registration capture Request for slap device type with two thumbs except left thumb finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
9 | SBI1008 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Both Exception | Valid Registration capture Request for slap device type with two thumbs except right thumb finger and left thumb finger | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
10 | SBI1009 | No | No | No | Yes | No | No | Registration capture - Double Iris | Valid Registration capture Request | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
11 | SBI1010 | No | No | No | Yes | No | No | Registration capture - Double Iris - One Exception | Valid Registration capture Request for Double iris device type except left iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
12 | SBI1011 | No | No | No | Yes | No | No | Registration capture - Double Iris - Both Exception | Valid Registration capture Request for Double iris device type except left iris and right iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
13 | SBI1012 | No | No | No | No | Yes | No | Registration capture - Face | Valid Registration capture Request only for Face | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
14 | SBI1013 | No | No | No | No | Yes | No | Registration capture - Exception Photo | Valid Registration capture Request for Face device type exception value left little finger or any will give Exception photo | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
15 | SBI1014 | No | Yes | No | No | No | No | Auth capture - Face | Valid Auth capture Request only for Face | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
16 | SBI1015 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris | Valid Auth capture Request for Unknown iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
17 | SBI1016 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris | Valid Auth capture Request for Left iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
18 | SBI1017 | Yes | No | No | No | No | No | Auth capture - Single Iris - Right Iris | Valid Auth capture Request for Right iris | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
19 | SBI1018 | No | No | Yes | No | No | No | Auth capture - Unknown Finger | Valid Auth capture Request for Unknown Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
20 | SBI1019 | No | No | Yes | No | No | No | Auth capture -Two Unknown Finger | Valid Auth capture Request for Two Unknown Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
21 | SBI1020 | No | No | Yes | No | No | No | Auth capture - LeftIndex Finger | Valid Auth capture Request for LeftIndex Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
22 | SBI1021 | No | No | Yes | No | No | No | Auth capture - Two Finger | Valid Auth capture Request for Two Finger | SchemaValidator SignatureValidator ResponseMismatchValidator | ResponseMismatchValidator | Available | ResponseMismatchValidator newly added available in 1.0.0-b2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
23 | SBI1022 | No | No | No | No | No | Yes | Registration capture - Key Rotation - Left Slap | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
24 | SBI1023 | Yes | No | No | No | No | No | Auth capture -Key Rotation - Single Iris - Left Iris | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
25 | SBI1024 | No | No | Yes | No | No | No | Auth capture - Key Rotation - LeftIndex Finger | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
26 | SBI1025 | No | Yes | No | No | No | No | Auth capture - Face - Key Rotation | Test for device key rotation | KeyRotationValidator | Key Rotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
27 | SBI1026 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Ready | Test to validate Device Info interface for a device that is in Ready state | SchemaValidator |  | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
28 | SBI1027 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Busy | Test to validate if the device is in Busy state | SchemaValidator | Device Status | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
29 | SBI1028 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Not Ready | Test to validate if the device is in Not Ready state | SchemaValidator | Device Status | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
30 | SBI1029 | Yes | Yes | Yes | Yes | Yes | Yes | Check Device Status - Not Registered | Test to validate if the device is in Not Registered state | SchemaValidator | Device Status | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Yes
31 | SBI1030 | No | No | Yes | No | No | No | Auth capture - Fingerprint - Bio Count Mismatch | Test to validate bio count mismatch for auth fingerprint device | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
32 | SBI1031 | Yes | No | No | No | No | No | Auth capture - Iris - Bio Count Mismatch | Test to validate bio count mismatch for auth iris device | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
33 | SBI1032 | No | Yes | No | No | No | No | Auth capture - Face - Bio Count Mismatch | Test to validate bio count mismatch for face | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
34 | SBI1033 | No | No | No | No | No | Yes | Registration capture - Left Slap - Bio Count Mismatch | Test to validate bio count mismatch for registration left slap | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
35 | SBI1034 | No | No | No | No | No | Yes | Registration capture - Right Slap - Bio Count Mismatch | Test to validate bio count mismatch for registration right slap | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
36 | SBI1035 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Bio Count Mismatch | Test to validate bio count mismatch for registration thumbs | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
37 | SBI1036 | No | No | No | Yes | No | No | Registration capture - Left iris - Bio Count Mismatch | Test to validate bio count mismatch for registration left iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
38 | SBI1037 | No | No | No | Yes | No | No | Registration capture - Right Iris - Bio Count Mismatch | Test to validate bio count mismatch for registration right iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
39 | SBI1038 | No | No | No | Yes | No | No | Registration capture - Both Iris - Bio Count Mismatch | Test to validate bio count mismatch for registration both iris | SchemaValidator |  | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
40 | SBI1039 | No | No | No | No | Yes | No | Registration capture - Face - Bio Count Mismatch | Test to validate bio count mismatch for registration face | SchemaValidator |  | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
41 | SBI1040 | No | No | No | No | Yes | No | Registration capture - Face - Timeout | Test to validate face timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
42 | SBI1042 | No | No | No | No | No | Yes | Registration capture - Left Slap - Timeout | Test to validate left slap timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
43 | SBI1043 | No | No | No | No | No | Yes | Registration capture - Right Slap - Timeout | Test to validate right slap timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
44 | SBI1044 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Timeout | Test to validate thumb timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
45 | SBI1041 | No | No | No | Yes | No | No | Registration capture - Double Iris - Timeout | Test to validate iris timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
46 | SBI1045 | No | No | No | No | Yes | No | Registration capture - Exception Photo - Timeout | Test to validate exception photo timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
47 | SBI1051 | No | No | No | No | No | Yes | Registration capture - Left Slap - Force Capture | Force Capture validation for registration capture request for Left Slap | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
48 | SBI1052 | No | No | No | No | No | Yes | Registration capture - Right Slap - Force Capture | Force Capture validation for registration capture request for Right Slap | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
49 | SBI1053 | No | No | No | No | No | Yes | Registration capture - Two Thumbs - Force Capture | Force Capture validation for registration capture request for Two Thumbs | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
50 | SBI1050 | No | No | No | Yes | No | No | Registration capture - Double Iris - Force Capture | Force Capture validation for registration capture request for double iris | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
51 | SBI1049 | No | No | No | No | Yes | No | Registration capture - Face - Force Capture | Force Capture validation for registration capture request for face | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
52 | SBI1054 | No | No | No | No | Yes | No | Registration capture - Exception Photo - Force Capture | Force Capture validation for Face device type exception value left little finger or any will give Exception photo | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
53 | SBI1057 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Force Capture | Force Capture validation for Auth capture Request for Unknown Finger | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
54 | SBI1056 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris - Force Capture | Force Capture validation for Auth capture Request for Unknown iris | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
55 | SBI1055 | No | Yes | No | No | No | No | Auth capture - Face - Force Capture | Force Capture validation for Auth capture Request only for Face | SchemaValidator TimeoutValidator SignatureValidator | Force Capture | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
56 | SBI1048 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Timeout | Test to validate finger timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
57 | SBI1047 | Yes | No | No | No | No | No | Auth capture - Single Iris - Unknown Iris - Timeout | Test to validate iris timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
58 | SBI1046 | No | Yes | No | No | No | No | Auth capture - Face - Timeout | Test to validate face timeout | SchemaValidator TimeoutValidator | Timeout | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
59 | SBI1058 | No | No | Yes | No | No | No | Auth capture - 10 Fingers | Test to perform Auth capture for 10 Fingers | SchemaValidator ResponseMismatchValidator SignatureValidator | ResponseMismatchValidator | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
60 | SBI1059 | Yes | No | No | No | No | No | Auth capture - 2 Iris | Test to perform Auth capture for 2 Iris | SchemaValidator ResponseMismatchValidator SignatureValidator | ResponseMisMatchValidator | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
61 | SBI1060 | No | No | No | No | Yes | No | Registration capture - Key Rotation - Face | Test for device key rotation | KeyRotationValidator | KeyRotation | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
62 | SBI1061 | No | No | No | Yes | No | No | Registration capture - Key Rotation - Double Iris | Test for device key rotation | KeyRotationValidator | KeyRotation | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
63 | SBI1062 | No | No | No | No | No | Yes | Registration capture - Left Slap - ISO Standard Validations | Test to validate the RCapture interface for Left Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
64 | SBI1063 | No | No | No | No | No | Yes | Registration capture - Right Slap - ISO Standard Validations | Test to validate RCapture interface for Right Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
65 | SBI1064 | No | No | No | Yes | No | No | Registration capture - Double Iris - ISO Standard Validations | Test to validate RCapture interface for Two Iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
66 | SBI1065 | No | No | No | No | Yes | No | Registration capture - Face - ISO Standard Validations | Test to validate RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
67 | SBI1066 | No | Yes | No | No | No | No | Auth capture - Face - ISO Standard Validations | Test to validate Capture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
68 | SBI1067 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris - ISO Standard Validations | Test to validate Capture interface for left iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
69 | SBI1068 | Yes | No | No | No | No | No | Auth capture - Single Iris - Right Iris - ISO Standard Validations | Test to validate Capture interface for right iris | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
70 | SBI1069 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - ISO Standard Validations | Test to validate Capture interface for a finger | SchemaValidator SignatureValidator ResponseMismatchValidator ISOStandardsValidator | ISOStandards | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
71 | SBI1070 | No | No | No | No | No | No | Streaming test with Registration capture - Left Slap | Streaming Test to validate the RCapture interface for Left Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
72 | SBI1071 | No | No | No | No | No | No | Streaming test with Registration capture - Right Slap | Streaming Test to validate the RCapture interface for Right Slap Fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
73 | SBI1072 | No | No | No | No | No | No | Streaming test with Registration capture - Two Thumbs | Streaming Test to validate the RCapture interface for Two Thumbs | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
74 | SBI1073 | No | No | No | No | No | No | Streaming test with Registration capture - Double Iris | Streaming Test to validate the RCapture interface for Two Iris | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
75 | SBI1074 | No | No | No | No | No | No | Streaming test with Registration capture - Face | Streaming Test to validate the RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator | Streaming | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
76 | SBI1075 | No | No | No | No | No | Yes | Biometrics Quality Check for Registration capture - Left Slap | Quality Check Test to validate the biometrics captured by RCapture interface for left slap fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
77 | SBI1076 | No | No | No | No | No | Yes | Biometrics Quality Check for Registration capture - Right Slap | Quality Check Test to validate the biometrics captured by RCapture interface for right slap fingerprints | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
78 | SBI1077 | No | No | No | Yes | No | No | Biometrics Quality Check for Registration capture - Double Iris | Quality Check Test to validate the biometrics captured by RCapture interface for both iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
79 | SBI1078 | No | No | No | No | Yes | No | Biometrics Quality Check for Registration capture - Face | Quality Check Test to validate the biometrics captured by RCapture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
80 | SBI1079 | No | Yes | No | No | No | No | Biometrics Quality Check for Auth capture - Face | Quality Check Test to validate the biometrics captured by Capture interface for face | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
81 | SBI1080 | Yes | No | No | No | No | No | Biometrics Quality Check for Auth capture - Single Iris - Left Iris | Quality Check Test to validate the biometrics captured by Capture interface for left iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
82 | SBI1081 | Yes | No | No | No | No | No | Biometrics Quality Check for Auth capture - Single Iris - Right Iris | Quality Check Test to validate the biometrics captured by Capture interface for right iris | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
83 | SBI1082 | No | No | Yes | No | No | No | Biometrics Quality Check for Auth capture - Unknown Finger | Quality Check Test to validate the biometrics captured by Capture interface for a finger | SchemaValidator SignatureValidator ResponseMismatchValidator BiometricsQualityCheckValidator | Biometrics Quality Check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
84 | SBI1083 | No | No | No | No | No | Yes | Time Check for Registration capture - Left Slap | Test to validate the timestamp captured by RCapture interface for left slap fingerprints | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
85 | SBI1084 | No | No | No | No | No | Yes | Time Check for Registration capture - Right Slap | Test to validate the timestamp captured by RCapture interface for right slap fingerprints | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | Yes
86 | SBI1085 | No | No | No | Yes | No | No | Time Check for Registration capture - Double Iris | Test to validate the timestamp captured by RCapture interface for both iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | N/A | Yes
87 | SBI1086 | No | No | No | No | Yes | No | Time Check for Registration capture - Face | Test to validate the timestamp captured by RCapture interface for face | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | Fail | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | N/A | N/A | Yes
88 | SBI1087 | No | Yes | No | No | No | No | Time Check for Auth capture - Face | Test to validate the timestamp captured by Capture interface for face | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
89 | SBI1088 | Yes | No | No | No | No | No | Time Check for Auth capture - Single Iris - Left Iris | Test to validate the timestamp captured by Capture interface for left iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
90 | SBI1089 | Yes | No | No | No | No | No | Time Check for Auth capture - Single Iris - Right Iris | Test to validate the timestamp captured by Capture interface for right iris | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
91 | SBI1090 | No | No | Yes | No | No | No | Time Check for Auth capture - Unknown Finger | Test to validate the timestamp captured by Capture interface for a finger | SchemaValidator ResponseMismatchValidator SignatureValidator TimeCheckValidator | Time stamp check | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
92 | SBI1091 | No | Yes | No | No | No | No | Auth capture - Face - Invalid Transaction Id | Test to validate transactionId of Capture method for face | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | Yes
93 | SBI1092 | Yes | No | No | No | No | No | Auth capture - Single Iris - Left Iris - Invalid Transaction Id | Test to validate transactionId of Capture method for left iris | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | Yes
94 | SBI1093 | No | No | Yes | No | No | No | Auth capture - Unknown Finger - Invalid Transaction Id | Test to validate transactionId of Capture method for a finger | SchemaValidator ResponseMismatchValidator SignatureValidator | Invalid Transaction Id | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Pass | N/A | N/A | Yes
95 | SBI1094 | No | No | No | No | No | No | Registration capture - Left Slap - Invalid Request Json (wrong attribute name envXXX) | Test to validate invalid request json in RCapture method for Left Slap Fingerprints | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
96 | SBI1095 | No | No | No | No | No | No | Registration capture - Right Slap - Invalid Request Json (wrong attribute name timeoutXXX) | Test to validate invalid request json in RCapture method for Right Slap Fingerprints | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
97 | SBI1096 | No | No | No | No | No | No | Registration capture - Two Thumbs - Invalid Request Json (wrong attribute name specVersionXXX) | Test to validate invalid request json in RCapture method for Two Thumbs | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
98 | SBI1097 | No | No | No | No | No | No | Registration capture - Double Iris - Invalid Request Json (wrong attribute name purposeXXX) | Test to validate invalid request json in RCapture method for Two Iris | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
99 | SBI1098 | No | No | No | No | No | No | Registration capture - Face - Invalid Request Json (wrong attribute name bioXXX) | Test to validate invalid request json in RCapture method for face | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
100 | SBI1099 | No | No | No | No | No | No | Registration capture - Double Iris - One Exception - Invalid Request Json (wrong attribute name countXXX) | Test to validate invalid request json in RCapture method for iris with one missing iris | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No
101 | SBI1100 | No | No | No | No | No | No | Registration capture - Exception Photo - Invalid Request Json (wrong attribute name deviceSubIdXXX) | Test to validate invalid request json in RCapture method for exception photo | SchemaValidator | Invalid Request Json | Available |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No

## Issues
Bug ID | Summary | Severity | Status | Remarks
MOSIP-27391 | CTK - UI and Buttons not aligned properly | Minor | Assigned
MOSIP-26762 | Newly registered user not landing in to CTK android home page. | Critical | Tetsing | Intermittent issue, Need to cross check in different devices
MOSIP-27304 | In Android CTK -'Encryption Key' button is not appearing for Auth projects | Major | Assigned | Partner can download Encryption Key from windows CTK
MOSIP-27257 | While initial launch Android mock SBI is not landing into home page | Major | Assigned
MOSIP-27044 | In CTK Android app UI elements are overlapping with each other. | Major | Assigned
MOSIP-27060 | Testcases failing in android CTK with NPrime-AndroidRegFaceSBI | Critical | New | Vendor Issue
MOSIP-26993 | Unable to scan face camera with NPrime Face Registration MDS in android CTK | Critical | To be fixed | Vendor Issue
MOSIP-26898 | After login to CTK android app, the previous browser tab is not killed | Major | Testing | Need Rounak inputs