## Base platform verification
Scenario(s) verification
Module | Scenarios | Mock MDS | Status | Notes | Tested with Components
Admin | Data setup (Master data, Machine (TPM Utility), center and operator mapping) |  | Passed |  | Mock MDS 1.2.0-SNAPSHOT for Reg and Auth
Registration Client (1.1.4) | Initial launch - Login (PWD), Different user in the same machine, Logout, Reset Password,Forgot username |  | Passed |  | Mock MDS 1.2.1-SNAPSHOT for Reg and Auth
| First user Registration (Default User) | 1.2.0-SNAPSHOT | Passed |  | kernel-auth-service': 'mosipqa/kernel-auth-service:1.1.5.5-P2'
| Remove Default role- Operator On boarding | 1.2.0-SNAPSHOT | Passed |  | kernel-masterdata-service': 'mosipqa/kernel-masterdata-service:1.1.5.3-P2'
| Update Operator Biometrics | 1.2.0-SNAPSHOT | Passed |  | kernel-idgenerator-service': 'mosipid/kernel-idgenerator-service:1.1.5.5'
| User Roles - Default, Reg_Supervisor and Reg_Officer |  | Failed | MOSIP-27217 -Will not fix. As fix is already available in 1.1.5.5) | kernel-pridgenerator-service': 'mosipid/kernel-pridgenerator-service:1.1.5.5'
| Registration flow - Demogarphics, Document Upload with Ref Numbers, Biometrics, Preview and Acknoledgement. | 1.2.0-SNAPSHOT | Passed |  | kernel-syncdata-service': 'mosipqa/kernel-syncdata-service:1.1.5.3-P2'
| Registrations Flows: New: Adult,AdultExceptionLeftEye, NewAdultExceptionFP, ChildInfant, Child ExceptionEyeParent Update: Adult demo, Adult Bio, Adult Bio Exception, AdultDemoBioDoc, UpdateAdultDocs. | 1.2.0-SNAPSHOT | Passed |  | kernel-auditmanager-service': 'mosipqa/kernel-auditmanager-service:1.1.5.5-P1'
| With PRID: Based on age - Child and Adult. Based on PRID status Booked, incomplete, Pending, Cancelled & Expired and only with mandatory fields, with mandatory & optional fields. | 1.2.0-SNAPSHOT | NA |  | kernel-keymanager-service': 'mosipqa/kernel-keymanager-service:1.1.5.5-P1'
| Lost registartion flow. | 1.2.0-SNAPSHOT | Passed |  | kernel-notification-service': 'mosipdev/kernel-notification-service:1.1.5.5'
| With exceptions: Adult exception Iris/FP (exception biometrics image), Infant exception -Parent Iris/FP, | 1.2.0-SNAPSHOT | Passed |  | kernel-otpmanager-service': 'mosipdev/kernel-otpmanager-service:1.1.5.5'
| Update Registartion flow - Adult: Demo & Biometrics, | 1.2.0-SNAPSHOT | Passed |  | kernel-ridgenerator-service': 'mosipdev/kernel-ridgenerator-service:1.1.5.5'
| Update Child packet to Adult packet scenarios | 1.2.0-SNAPSHOT | Passed |  | kernel-keys-generator': 'mosipdev/keys-generator:1.1.5.3'
| EoD (Pending Approval/Rajected and DashBoard) | 1.2.0-SNAPSHOT | Passed |  | prereg-application-service': 'mosipid/pre-registration-application-service:1.1.5.3'
| Application Upload | 1.2.0-SNAPSHOT | Passed |  | prereg-batchjob-service': 'mosipqa/pre-registration-batchjob:1.1.5.3'
| packets export/Save to Device in online/offline mode. | 1.2.0-SNAPSHOT | Passed |  | prereg-booking-service': 'mosipqa/pre-registration-booking-service:1.1.5.5-P3'
| Synchronize Data | 1.2.0-SNAPSHOT | Passed |  | prereg-datasync-service': 'mosipqa/pre-registration-datasync-service:1.1.5.3'
| Download Pre Registration Data | 1.2.0-SNAPSHOT | NA |  | prereg-captcha-service': 'mosipid/pre-registration-captcha-service:1.1.5.3'
| Upgrading Reg.Client from 1.1.4 to 1.1.5.5 | 1.2.0-SNAPSHOT | Passed |  | prereg-ui': 'mosipid/pre-registration-ui:1.1.5.3'
| Backup' scenario if upgrade fails |  | Passed |  | reg-client-downloader': 'mosipqa/registration-client:1.1.5.5'
| Upgrading Reg.Client from 1.1.4 to 1.2.0 |  | Pending | Have to test after upgrading server to 1.2.0.1 | regproc-camel-stage': 'mosipqa/registration-processor-common-camel-bridge:1.1.5.5-P3'
Reg Proc | Packet Receiver stage to Finalization stages | 1.2.0-SNAPSHOT | Passed |  | regproc-securezone-notification-stage': 'mosipqa/registration-processor-securezone-notification-stage:1.1.5.5-P3'
| UIN generation for Supervisor Approved/Rejected Packets | 1.2.0-SNAPSHOT | Passed |  | regproc-packet-uploader-stage': 'mosipqa/registration-processor-packet-uploader-stage:1.1.5.5-P3'
| Email Notification based on prefered language | 1.2.0-SNAPSHOT | Passed |  | regproc-quality-checker-stage': 'mosipqa/registration-processor-quality-checker-stage:1.1.5.5-P3'
IDA using APIs | Demographic authentication of Infant/adult UIN |  | Passed |  | regproc-packet-validator-stage': 'mosipqa/registration-processor-packet-validator-stage:1.1.5.5-P3'
| Infant(Only Face) updated to Adult(all biometrics captured) then authentication with all biometrics |  | Passed |  | regproc-osi-validator-stage': 'mosipid/registration-processor-osi-validator-stage:1.1.5.6'
| demo/bio authentication using VID |  | Passed |  | regproc-demo-dedupe-stage': 'mosipqa/registration-processor-demo-dedupe-stage:1.1.5.5-P3'
| Biometric authentication of adult UIN |  | Passed |  | regproc-bio-dedupe-stage': 'mosipqa/registration-processor-bio-dedupe-stage:1.1.5.5-P3'
| Authentication using OTP |  | Passed |  | regproc-biometric-authentication-stage': 'mosipqa/registration-processor-biometric-authentication-stage:1.1.5.5-P3'
| Ekyc authentication |  | Passed |  | regproc-abis-handler-stage': 'mosipqa/registration-processor-abis-handler-stage:1.1.5.5-P3'
| Email Notifications |  | Passed |  | regproc-abis-middleware-stage': 'mosipqa/registration-processor-abis-middleware-stage:1.1.5.5-P3'
| Authlock/unlock from resident |  | Passed |  | regproc-manual-verification-stage': 'mosipqa/registration-processor-manual-verification-stage:1.1.5.5-P3'
Resident | Request for otp using infant/adult UIN |  | Passed |  | regproc-external-stage': 'mosipqa/registration-processor-external-stage:1.1.5.5-P3'
| Generate VID using infant/adult UIN |  | Passed |  | regproc-external-integration-service': 'mosipqa/registration-processor-external-integration-service:1.1.5.5-P3'
| Revoke VID |  | Passed |  | regproc-uin-generator-stage': 'mosipqa/registration-processor-uin-generator-stage:1.1.5.5-P3'
| Request for credential from UIn/VID |  | Passed |  | regproc-message-sender-stage': 'mosipqa/registration-processor-message-sender-stage:1.1.5.5-P3'
| Download card for infant/adult UIN |  | Passed |  | regproc-printing-stage': 'mosipqa/registration-processor-printing-stage:1.1.5.5-P3'
| Update Infant/adult UIN |  | Passed |  | regproc-registration-transaction-service': 'mosipqa/registration-processor-registration-transaction-service:1.1.5.5-P3'
| Lock/unlock UIN |  | Passed |  | regproc-reprocessor-stage': 'mosipqa/registration-processor-reprocessor-stage:1.1.5.5-P3'
| Auth history |  | Passed |  | regproc-packet-receiver-stage': 'mosipid/registration-processor-packet-receiver-stage:1.1.5.5-P3'
PMS | Create policy group and polices |  | Passed |  | regproc-camel-stage': 'mosipqa/registration-processor-common-camel-bridge:1.1.5.5-P3'
| Self register for partner |  | Passed | MOSIP-27181 - We will not fix this in 1.1.5.5. | regproc-registration-status-service': 'mosipqa/registration-processor-registration-status-service:1.1.5.5-P3'
| Upload certificates and generate API key |  | Passed |  | regproc-dmz-packet-server': 'mosipqa/registration-processor-dmz-packet-server:1.1.5.5-P3'
| Misp partner registration and MISP license key generation |  | Passed |  | ida-auth-service': 'mosipqa/authentication-service:1.1.5.5-P1'
Registration Client (1.1.5.5) | Initial launch - Login (PWD), Different user in the same machine, Logout | 1.2.0-SNAPSHOT | Passed |  | ida-internal-service': 'mosipqa/authentication-internal-service:1.1.5.5-P1'
| First user Registration (Default User) | 1.2.0-SNAPSHOT | Passed |  | ida-kyc-service': 'mosipqa/authentication-kyc-service:1.1.5.5-P1'
| Remove Default role- Operator On boarding | 1.2.0-SNAPSHOT | Passed |  | ida-otp-service': 'mosipqa/authentication-otp-service:1.1.5.5-P1'
| User Roles - Default, Reg_Supervisor and Reg_Officer | 1.2.0-SNAPSHOT | Passed |  | ida-key-generator': 'mosipid/keys-generator:1.1.5'
| Registration flow - Demogarphics, Document Upload with Ref Numbers, Biometrics, Preview and Acknoledgement. | 1.2.0-SNAPSHOT | Passed |  | idrepo-identity-service': 'mosipqa/id-repository-identity-service:1.1.5.5-P2'
| Registrations Flows: New: Adult,AdultExceptionLeftEye, NewAdultExceptionFP, ChildInfant, Child ExceptionEyeParent | 1.2.0-SNAPSHOT 1.2.1-SNAPSHOT | Passed |  | idrepo-vid-service': 'mosipqa/id-repository-vid-service:1.1.5.5-P2'
| With PRID: Based on age - Child and Adult. Based on PRID status Booked & Expired and only with mandatory fields, with mandatory & optional fields. | 1.2.0-SNAPSHOT 1.2.1-SNAPSHOT | Passed |  | idrepo-credential-request-generator': 'mosipid/credential-request-generator:1.1.4.4-P1'
| Lost registeration flow. | 1.2.0-SNAPSHOT | Passed |  | idrepo-credential-service': 'mosipqa/credential-service:1.1.5.5-P2'
| With exceptions: Adult exception Iris/FP (exception biometrics image), Infant exception -Parent Iris/FP, | 1.2.0-SNAPSHOT 1.2.1-SNAPSHOT | Passed |  | idrepo-salt-generator': 'mosipqa/id-repository-salt-generator:1.1.5.5-P2'
| Update: Adult demo, Adult Bio, Adult Bio Exception, AdultDemoBioDoc, UpdateAdultDocs. | 1.2.0-SNAPSHOT 1.2.1-SNAPSHOT | Passed |  | pms-partner-manager-service': 'mosipqa/partner-management-service:1.1.5.4-P2'
| Update Child packet to Adult packet scenarios | 1.2.0-SNAPSHOT 1.2.1-SNAPSHOT | Passed |  | pms-policy-manager-service': 'mosipqa/policy-management-service:1.1.5.4-P2'
| EoD (Pending Approval/Rajected) | 1.2.0-SNAPSHOT | Passed |  | resident-service': 'mosipqa/resident-service:1.1.5.4'
| Application Upload | 1.2.0-SNAPSHOT | Passed |  | admin-service': 'mosipqa/admin-service:1.1.5.3-P2'
| packets export/Save to Device in online/offline mode. | 1.2.0-SNAPSHOT | Passed |  | admin-ui': 'mosipid/admin-ui:1.1.5'
| Synchronize Data | 1.2.0-SNAPSHOT | Passed |  | packetmanager-service': 'mosipqa/commons-packet-service:1.1.5.5-P1'
| Center Remapping | 1.2.0-SNAPSHOT | Passed |  | datashare-service': 'mosipqa/data-share-service:1.1.5.3-P2'
| Download Pre Registration Data | 1.2.0-SNAPSHOT | Passed |  | print-service': 'mosipqa/print:1.1.5.4'
| Operator login with FP, Iris and Face (Login, Packet Auth, Reviewer Auth, EoD auth). | 1.2.0-SNAPSHOT | Passed |  | websub-service': 'mosipid/websub-service:1.1.5.3'
| Upgrading Reg.Client from 1.1.5 to 1.2.0 |  | Pending | Have to test after upgrading server to 1.2.0.1 | consolidator-websub-service': 'mosipid/consolidator-websub-service:1.1.5.3'
| Backup' scenario if upgrade fails |  | Pending | Have to test after upgrading server to 1.2.0.1 | mock-abis': 'mosipid/mock-abis:1.2.0.1-B2'
IDA using Auth UI | Demographic authentication of Infant/adult UIN |  | Passed |  | mock-mv': 'mosipid/mock-mv:1.2.0.1-B2'
| Bio face authentication with adult UIN |  | Passed |  | mock-biosdk-service': 'mosipid/biosdk-server:1.2.0.1-B2'
| Bio iris/finger authentication with adult UIN |  | Passed |  | artifactory-service': 'mosipqa/artifactory-server:1.1.5.5-P1'
| demo authentication using VID |  | Passed |  | mosip_file_server': 'mosipid/mosip-file-server:1.1.5_v2'
| bio face authentication using VID |  | Passed |  | resident-app-server': 'mosipid/mimoto:1.1.5'
| bio iris/finger authentication using VID |  | Passed
| Authentication using OTP |  | Passed
| Ekyc authentication for demo |  | Passed
| Ekyc authentication for Bio face |  | Passed
| Ekyc authentication for Bio iris/finger |  | Passed
| Email Notifications |  | Passed
| Authlock/unlock from resident |  | Passed

## Open Issues
JIRA | Issue Detail | Status | Addressed By | Fix Details | Remarks
MOSIP-27217 | After removing the default role, the user still goes to the RegClient homepage. | Cancelled | Rounak | We will not fix this. As fix is already available in 1.1.5.5
MOSIP-27219 | Captured guardian Fingerprint data is not displayed when we return from the preview window. | Cancelled | Rounak | We will not fix this in Reg.Client 1.1.4. In Reg.Client 1.1.5.5 working as expected.
MOSIP-27376 | Unable to capture biometrics, after upgrading Reg.Client from 1.1.4 to 1.1.5.5 | Closed | Himaja
MOSIP-27181 | PMP API: 'Self Registration Partner' created with invalid contact number. | Cancelled | Rounak | We will not fix this in 1.1.5.5.
MOSIP-27363 | Auth UI(IDA): Unable to perform authentication for Finger and Iris. | Cancelled | Rounak | We will not fix it.
MOSIP-27244 | Certificates are not moving to Ida ca cert table from Keymanager ca cert table | Cancelled | Rounak | No need to fix this in 1.1.5.5
MOSIP-27389 | Prereg - Unable to fetch data for Pending PRIDs | Cancelled | Rounak
MOSIP-27671 | Unable to uploaded unsynced packets from Admin portal | New | Balaji

## 1155 Docker Versions (hidden)
# Manifest file containing version of all MOSIP core components.
versions:
services:
kernel:
auth:
kernel-auth-service': 'mosipqa/kernel-auth-service:1.1.5.5-P2'
masterdata:
kernel-masterdata-service': 'mosipqa/kernel-masterdata-service:1.1.5.3-P2'
idgen:
kernel-idgenerator-service': 'mosipid/kernel-idgenerator-service:1.1.5.5'
prid:
kernel-pridgenerator-service': 'mosipid/kernel-pridgenerator-service:1.1.5.5'
sync:
kernel-syncdata-service': 'mosipqa/kernel-syncdata-service:1.1.5.3-P2'
audit :
kernel-auditmanager-service': 'mosipqa/kernel-auditmanager-service:1.1.5.5-P1'
key:
kernel-keymanager-service': 'mosipqa/kernel-keymanager-service:1.1.5.5-P1'
notifier:
kernel-notification-service': 'mosipdev/kernel-notification-service:1.1.5.5'
otp:
kernel-otpmanager-service': 'mosipdev/kernel-otpmanager-service:1.1.5.5'
rid:
kernel-ridgenerator-service': 'mosipdev/kernel-ridgenerator-service:1.1.5.5'
keygen:
kernel-keys-generator': 'mosipdev/keys-generator:1.1.5.3'
prereg:
application:
prereg-application-service': 'mosipid/pre-registration-application-service:1.1.5.3'
batch:
prereg-batchjob-service': 'mosipqa/pre-registration-batchjob:1.1.5.3'
booking:
prereg-booking-service': 'mosipqa/pre-registration-booking-service:1.1.5.5-P3'
datasync:
prereg-datasync-service': 'mosipqa/pre-registration-datasync-service:1.1.5.3'
captcha:
prereg-captcha-service': 'mosipid/pre-registration-captcha-service:1.1.5.3'
ui:
prereg-ui': 'mosipid/pre-registration-ui:1.1.5.3'
registration_client:
downloader:
reg-client-downloader': 'mosipqa/registration-client:1.1.5.5'
version: 1.1.5.5
regproc:
camel:
regproc-camel-stage': 'mosipqa/registration-processor-common-camel-bridge:1.1.5.5-P3'
notification:
regproc-securezone-notification-stage': 'mosipqa/registration-processor-securezone-notification-stage:1.1.5.5-P3'
uploader:
regproc-packet-uploader-stage': 'mosipqa/registration-processor-packet-uploader-stage:1.1.5.5-P3'
quality:
regproc-quality-checker-stage': 'mosipqa/registration-processor-quality-checker-stage:1.1.5.5-P3'
validator:
regproc-packet-validator-stage': 'mosipqa/registration-processor-packet-validator-stage:1.1.5.5-P3'
osi:
regproc-osi-validator-stage': 'mosipid/registration-processor-osi-validator-stage:1.1.5.6'
demo:
regproc-demo-dedupe-stage': 'mosipqa/registration-processor-demo-dedupe-stage:1.1.5.5-P3'
bio:
regproc-bio-dedupe-stage': 'mosipqa/registration-processor-bio-dedupe-stage:1.1.5.5-P3'
bioauth:
regproc-biometric-authentication-stage': 'mosipqa/registration-processor-biometric-authentication-stage:1.1.5.5-P3'
abishandler:
regproc-abis-handler-stage': 'mosipqa/registration-processor-abis-handler-stage:1.1.5.5-P3'
abismid:
regproc-abis-middleware-stage': 'mosipqa/registration-processor-abis-middleware-stage:1.1.5.5-P3'
manual:
regproc-manual-verification-stage': 'mosipqa/registration-processor-manual-verification-stage:1.1.5.5-P3'
external:
regproc-external-stage': 'mosipqa/registration-processor-external-stage:1.1.5.5-P3'
eis:
regproc-external-integration-service': 'mosipqa/registration-processor-external-integration-service:1.1.5.5-P3'
uin:
regproc-uin-generator-stage': 'mosipqa/registration-processor-uin-generator-stage:1.1.5.5-P3'
msg:
regproc-message-sender-stage': 'mosipqa/registration-processor-message-sender-stage:1.1.5.5-P3'
print:
regproc-printing-stage': 'mosipqa/registration-processor-printing-stage:1.1.5.5-P3'
trans:
regproc-registration-transaction-service': 'mosipqa/registration-processor-registration-transaction-service:1.1.5.5-P3'
reprocess:
regproc-reprocessor-stage': 'mosipqa/registration-processor-reprocessor-stage:1.1.5.5-P3'
dmzregproc:
receiver:
regproc-packet-receiver-stage': 'mosipid/registration-processor-packet-receiver-stage:1.1.5.5-P3'
camel:
regproc-camel-stage': 'mosipqa/registration-processor-common-camel-bridge:1.1.5.5-P3'
status:
regproc-registration-status-service': 'mosipqa/registration-processor-registration-status-service:1.1.5.5-P3'
pktserver:
regproc-dmz-packet-server': 'mosipqa/registration-processor-dmz-packet-server:1.1.5.5-P3'
ida:
auth:
ida-auth-service': 'mosipqa/authentication-service:1.1.5.5-P1'
internal:
ida-internal-service': 'mosipqa/authentication-internal-service:1.1.5.5-P1'
kyc:
ida-kyc-service': 'mosipqa/authentication-kyc-service:1.1.5.5-P1'
otp:
ida-otp-service': 'mosipqa/authentication-otp-service:1.1.5.5-P1'
keygen:
ida-key-generator': 'mosipid/keys-generator:1.1.5'
idrepo:
identity:
idrepo-identity-service': 'mosipqa/id-repository-identity-service:1.1.5.5-P2'
vid:
idrepo-vid-service': 'mosipqa/id-repository-vid-service:1.1.5.5-P2'
credentialreq:
idrepo-credential-request-generator': 'mosipid/credential-request-generator:1.1.4.4-P1'
credentialservice:
idrepo-credential-service': 'mosipqa/credential-service:1.1.5.5-P2'
salt:
idrepo-salt-generator': 'mosipqa/id-repository-salt-generator:1.1.5.5-P2'
pms:
partner:
pms-partner-manager-service': 'mosipqa/partner-management-service:1.1.5.4-P2'
policy:
pms-policy-manager-service': 'mosipqa/policy-management-service:1.1.5.4-P2'
ui:
pms-ui': 'mosipint/pmp-ui:develop'
resident:
resident:
resident-service': 'mosipqa/resident-service:1.1.5.4'
admin:
service:
admin-service': 'mosipqa/admin-service:1.1.5.3-P2'
ui:
admin-ui': 'mosipid/admin-ui:1.1.5'
packetmanager:
service:
packetmanager-service': 'mosipqa/commons-packet-service:1.1.5.5-P1'
datashare:
service:
datashare-service': 'mosipqa/data-share-service:1.1.5.3-P2'
print:
service:
print-service': 'mosipqa/print:1.1.5.4'
websub:
service:
websub-service': 'mosipid/websub-service:1.1.5.3'
consolidator:
consolidator-websub-service': 'mosipid/consolidator-websub-service:1.1.5.3'
mock:
abis:
mock-abis': 'mosipid/mock-abis:1.2.0.1-B2'
mv:
mock-mv': 'mosipid/mock-mv:1.2.0.1-B2'
biosdk:
mock-biosdk-service': 'mosipid/biosdk-server:1.2.0.1-B2'
artifactory:
service:
artifactory-service': 'mosipqa/artifactory-server:1.1.5.5-P1'
mosip_file_server:
service:
mosip_file_server': 'mosipid/mosip-file-server:1.1.5_v2'
resident_app_server:
service:
resident-app-server': 'mosipid/mimoto:1.1.5'