## Verification - Summary
Details | Stories Tested | Test Cases | [5 empty] | iOS Based Testing |  |  |  |  | Browser Versions Used For Testing | Tested with Components
| Total | Total | With Stories | w/o Stories | Pass | Fail | Not tested | Story | Test Results |  |  |  | Chrome: Version 123.0.6312.124 | mosipdev/authentication-demo-service:develop
INJI Web | 9 | 89 | 81 | 8 | 57 | 21 | 11 | INJIWEB-36 | 14 | 13 |  | 1 | Firefox: Version 125.0.1 | mosipdev/automationtests:develop
[8 empty] | INJIWEB-37 | 7 | 7 |  |  | Edge: Version 124.0.2478.51 | mosipdev/dsl-orchestrator:develop
Total | 9 | 89 | 81 | 8 | 57 | 21 | 11 | INJIWEB-44 | 8 | 7 |  | 1 | Safari : Version 16.6 | mosipdev/dsl-packetcreator:develop
[8 empty] | INJIWEB-45 | 19 | 9 | 10 |  |  | mosipdev/partner-onboarder:develop
[8 empty] | INJIWEB-47 | 6 | 3 | 3 |  |  | mosipdev/postgres-init:develop
[8 empty] | INJIWEB-48 | 8 | 4 |  | 4 |  | mosipid/activemq-artemis:1.1.5
Functional Testing - Stories Verified : 9 | [7 empty] | INJIWEB-49 | 6 | 6 |  |  |  | mosipid/admin-service:1.2.0.1-B1
Test cases : 89 Passed : 57 Failed : 21 Skipped : 11 | [7 empty] | INJIWEB-50 | 8 | 8 |  |  |  | mosipid/admin-ui:1.2.0.1-B1
Test Rate : 87% With Pass Rate : 73% | [7 empty] | INJIWEB-51 | 5 |  |  | 5 |  | mosipid/artifactory-server:1.4.0-ES
mosipid/authentication-internal-service:1.2.0.1
mosipid/authentication-otp-service:1.2.0.1
mosipid/authentication-service:1.2.0.1
mosipid/biosdk-server:1.2.0.1
mosipid/commons-packet-service:1.2.0.1-B1
mosipid/config-server:1.1.2
mosipid/consolidator-websub-service:1.2.0.1-B1
mosipid/data-share-service:1.2.0.1-B1
mosipid/esignet:1.4.0
mosipid/hotlist-service:1.2.0.1-B1
mosipid/id-repository-salt-generator:1.2.0.1-B2
mosipid/kernel-auth-service:1.2.0.1-B2
mosipid/kernel-idgenerator-service:1.2.0.1-B1
mosipid/kernel-keymanager-service:1.2.0.1-B2
mosipid/kernel-notification-service:1.2.0.1-B1
mosipid/kernel-otpmanager-service:1.2.0.1-B1
mosipid/kernel-pridgenerator-service:1.2.0.1-B1
mosipid/kernel-ridgenerator-service:1.2.0.1-B1
mosipid/kernel-salt-generator:1.2.0.1-B2
mosipid/kernel-syncdata-service:1.2.0.1-B1
mosipid/keycloak-init:1.2.0.1
mosipid/keycloak-init:1.2.0.1-B2
mosipid/keycloak-init:1.2.0.1-B3
mosipid/keys-generator:1.2.0.1-B3
mosipid/masterdata-loader:1.2.0.1-B4
mosipid/mock-abis:1.2.0.1-B2
mosipid/mock-mv:1.2.0.1-B2
mosipid/mock-relying-party-service:0.9.1
mosipid/mock-relying-party-service:0.9.2
mosipid/mock-relying-party-ui:0.9.1
mosipid/mock-relying-party-ui:0.9.2
mosipid/oidc-ui:1.4.0
mosipid/partner-management-service:1.2.0.1-B3
mosipid/partner-onboarder:1.2.0.1-B4
mosipid/pmp-ui:1.2.0.1-B1
mosipid/policy-management-service:1.2.0.1-B3
mosipid/postgres-init:1.2.0.1-B4
mosipid/pre-registration-application-service:1.2.0.1-B1
mosipid/pre-registration-batchjob:1.2.0.1-B1
mosipid/pre-registration-booking-service:1.2.0.1-B1
mosipid/pre-registration-captcha-service:1.2.0.1-B1
mosipid/pre-registration-datasync-service:1.2.0.1-B1
mosipid/pre-registration-ui:1.2.0.1-B1
mosipid/print:1.2.0.1-B1
mosipid/registration-client:1.2.0.1-B1
mosipid/registration-processor-common-camel-bridge:1.2.0.1-B1
mosipid/registration-processor-dmz-packet-server:1.2.0.1-B1
mosipid/registration-processor-notification-service:1.2.0.1-B1
mosipid/registration-processor-registration-status-service:1.2.0.1-B1
mosipid/registration-processor-registration-transaction-service:1.2.0.1-B1
mosipid/registration-processor-reprocessor:1.2.0.1-B1
mosipid/registration-processor-stage-group-1:1.2.0.1-B1
mosipid/registration-processor-stage-group-2:1.2.0.1-B1
mosipid/registration-processor-stage-group-3:1.2.0.1-B2
mosipid/registration-processor-stage-group-4:1.2.0.1-B1
mosipid/registration-processor-stage-group-5:1.2.0.1-B1
mosipid/registration-processor-stage-group-6:1.2.0.1-B1
mosipid/registration-processor-workflow-manager-service:1.2.0.1-B1
mosipid/softhsm:v2
mosipid/websub-service:1.2.0.1-B1
mosipint/credential-request-generator:develop-DP
mosipint/credential-service:develop-DP
mosipint/digital-card-service:release-1.2.0.1-DP
mosipint/id-repository-identity-service:develop-DP
mosipint/id-repository-vid-service:develop-DP
mosipint/kernel-masterdata-service:develop-DP
mosipint/registration-processor-stage-group-7:develop-DP
mosipint/resident-service:develop-DP
mosipint/resident-ui:develop-DP
mosipqa/artifactory-server:1.4.0-ES
mosipqa/authentication-demo-service:develop
mosipqa/automationtests:develop
mosipqa/compliance-toolkit-service:1.2.0
mosipqa/compliance-toolkit-ui:1.2.0
mosipqa/dsl-orchestrator:develop
mosipqa/dsl-packetcreator:develop
mosipqa/esignet:1.4.x
mosipqa/inji-verify:develop
mosipqa/inji-web:develop
mosipqa/kernel-auditmanager-service:1.2.0.1
mosipqa/keycloak-init:develop
mosipqa/mimoto:develop
mosipqa/mock-identity-system:0.9.0
mosipqa/mock-relying-party-service:0.9.x
mosipqa/mock-relying-party-ui:0.9.x
mosipqa/mock-smtp:0.0.2
mosipqa/mosip-artemis-keycloak:develop
mosipqa/mosip-file-server:develop
mosipqa/oidc-ui:1.4.x
mosipqa/softhsm:v2

## Inji - Web - Test Cases
Story id | Story Title | TestCase_No | Functional | Feature | Prerequisite | Scenario | Steps | Expected Result | Pass/Fail | Automated | Automated In | Automation Comments | Bug id | Remarks | Environments
INJIWEB-36 | [UI] Inji Web - Launch Inji Web Home Page | INJIWEB-36_TC_01 |  | Inji Home page | 1. The Inji Web Home Page should be available in the appropriate URL in the environment specified. 2. Inji Web should have configured Header (logo) similar to Inji mobile, Footer (copyright information) 3. Non-functional links of About MOSIP, Playstore and Appstore icons on the header. | Open Inji web in diff browsers | 1. Open browser 2. Browse Inji Web Home Page in all the supported browsers Ex: Chrome, Firefox, Edge,Safari etc. | Inji web page should be opened in all the supported browsers without any errors | Pass
INJIWEB-36 |  | INJIWEB-36_TC_02 |  | Inji Home page |  | Verify Header(Logo), footer(Copy right) info | 1. Open Inji Web Home Page 2. Verify Header and footer information on home page in all the supported browsers Ex: Chrome, Firefox, Edge,Safari etc. | Proper header and footer inforamtion similar to Inji mobile app | Pass
INJIWEB-36 |  | INJIWEB-36_TC_03 |  | Inji Home page |  | Verify non-functional button on homepage | 1. Open inji web page 2. Verify Non-functional links of About MOSIP, Playstore and Appstore icons on the header. | Inji web header should contain non-functional link, like About MOSIP, Playstore and Appstore icons on the header. | NA
INJIWEB-36 |  | INJIWEB-36_TC_04 |  | Inji Home page |  | Open inji home page in multiple winodws | 1. Open inji web page 2. Browse home page 3. Open another browser window 4. Browse inji home page | Inji home page should be opened in all the windows with all the configured content | Pass
INJIWEB-36 |  | INJIWEB-36_TC_05 |  | Inji Home page |  | Open inji home page in multiple tabs | 1. Open browser 2. Browse inji home page 3. Open another browser tab 4. Browse inji home page | Inji home page should be opened in all the tabs with all the configured content | Pass
INJIWEB-36 |  | INJIWEB-36_TC_06 |  | Inji Home page |  | Open inji home page in multiple winodws of diff browsers | 1. Open browser 2. Browse inji home page 3. Open another browser window in diff browser 4. Browse inji home page | Inji home page should be opened in all the windows with all the configured content | Pass
INJIWEB-36 |  | INJIWEB-36_TC_07 |  | Inji Home page |  | Open inji home page in incognito window | 1. Open browser 2. Browse inji home page 3. Open another window in incognito mode 4. Browse inji home page | Inji home page should be opened incognito mode with all the configured content | Pass
INJIWEB-36 |  | INJIWEB-36_TC_08 |  | Inji Home page |  | Verify List of issuers on home page | 1. Open browser 2. Browse inji home page 3. Verify all the issuers as per configuration | Home page should be displayed with all the configured issuers details | Pass
INJIWEB-36 |  | INJIWEB-36_TC_09 |  | Inji Home page |  | Serach issuer with complete name | 1. Open browser 2. Browse inji home page 3. Search for an issuer with complete name | Home page should be displayed with all the configured issuers details | Pass
INJIWEB-36 |  | INJIWEB-36_TC_10 |  | Inji Home page |  | Search Issuer with partial string | 1. Open browser 2. Browse inji home page 3. Search for an issuer with partial string | Home page should be displayed with all the configured issuers details as per search string | Pass
INJIWEB-36 |  | INJIWEB-36_TC_11 |  | Inji Home page |  | Serach issuer with non-existing value | 1. Open browser 2. Browse inji home page 3. Search for an issuer with non-existing value | Home page should not display any issuers | Pass
INJIWEB-36 |  | INJIWEB-36_TC_12 |  | Inji Home page |  | Verify click functionality on selected issuer | 1. Open browser 2. Browse inji home page 3. Click on Issuer | Click button should be functional and should navigate to "Credential Type selection" screen | Pass
INJIWEB-36 |  | INJIWEB-36_TC_13 |  | Inji Home page |  | Verify error message when the server is not reachable | 1. Open browser 2. Browse inji home page 3. Make sure the site is down | A red colour toaster should apper for 5 mins about the server is down and “The service is currently unavailable now. Please try again later.” at the footer | Pass
INJIWEB-36 |  | INJIWEB-36_TC_14 |  | Inji Home page |  | Verify the error message when the list of issuers cannot be retrieved. | 1. Open browser 2. Browse inji home page 3. Click on Issuer | “No issuers found. Please try again later.” should apper at the Issuers list section | Pass
INJIWEB-37 | [UI ]Inji Web- Issuer selection in the “Home Page” | INJIWEB-37_TC_01 |  | Issuer selection in the “Home Page” | 1. The “Issuer Selection” in the Home page should be updated with the list of issuers in a clickable tile. 2. While loading the web page, an API call to issuers list should happen. 3. The list of issuers should be taken from the mimoto issuers config. | Verify that the issuer can be selected. | 1. Open browser 2. Browse inji home page 3. Click on Issuer | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_02 |  | Issuer selection in the “Home Page” |  | Verify that the issuer can be selected in diff browser windows | 1. Open browser 2. Browse inji home page 3. Open another browser window 4. Browse inji home page 5. Click on the issuer in both pages | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_03 |  | Issuer selection in the “Home Page” |  | Verify that the issuer can be selected in diff browser tabs | 1. Open browser 2. Browse inji home page 3. Open another browser tab 4. Browse inji home page 5. Click on Issuer in both tabs | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_04 |  | Issuer selection in the “Home Page” |  | Verify that the issuer can be selected in diff browser windows in diff browsers | 1. Open browser 2. Browse inji home page 3. Open another browser window in diff browser 4. Browse inji home page 5. Click on Issuer in both pages | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_05 |  | Issuer selection in the “Home Page” |  | Verify that the issuer can be selected in incongnito window | 1. Open browser 2. Browse inji home page 3. Open another window in incognito mode 4. Browse inji home page 5. Click on issuer in both normal and incongnito mode | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_06 |  | Issuer selection in the “Home Page” |  | Verify that the issuer can be selected after search operation | 1. Open browser 2. Browse inji home page 3. Search for an issuer with complete / partial name 4. Click on issuer | Issuer can be selected and page navigated to "Credential Type selection" screen in the same tab | Pass
INJIWEB-37 |  | INJIWEB-37_TC_07 |  | Issuer selection in the “Home Page” |  | Update mimoto issuers config and verify list updated as per config | 1. Update mimito config file for the specified branch 2. Restart the required services 3. Open the inji home page 4. Verify the issuere list 5. Select the new and previously available issuer | Updated and previously available issuers should be displayed. And all the issuers can be selected | Pass
INJIWEB-44 | [UI] Inji Web - Select the Credential type in the “Download Credential” page | INJIWEB-44_TC_01 | UI | Download Credential | 1. The “Download Credential” page should be updated with the list of credentials(from the chosen issuer) in a clickable tile. 2. The credential types should be taken from the well-known file published by the issuer/s. 3. The endpoint required to prove ownership of the data (i.e. to authenticate the holder (ARC type)) should be in the well-known file for a given certificate type. | Verify the crednetials are listed only for the selected issuer | 1. Open browser 2. Browse inji home page 3. Select the issuer | Credentials should be displayed for the selected issuer only | Pass
INJIWEB-44 |  | INJIWEB-44_TC_02 |  | Download Credential |  | Verify the "Credential download" diff browser windows | 1. Open browser 2. Browse inji home page 3. Select Issuer 4. Select Credential 3. Repeat the steps in another browser window | Credentials should be displayed for the selected issuers and Authentication Portal should be opened for authentication | Pass
INJIWEB-44 |  | INJIWEB-44_TC_03 |  | Download Credential |  | Verify the "Credential download" diff browser tabs | 1. Open browser 2. Browse inji home page 3. Select Issuer 4. Select Credential 3. Repeat the steps in another tab | Credentials should be displayed for the selected issuers and Authentication Portal should be opened for authentication | Pass
INJIWEB-44 |  | INJIWEB-44_TC_04 |  | Download Credential |  | Verify the "Credential download" in diff browser windows in diff browsers | 1. Open browser 2. Browse inji home page 3. Select Issuer 4. Select Credential 3. Repeat the steps in diff browsers | Credentials should be displayed for the selected issuers and Authentication Portal should be opened for authentication | Pass
INJIWEB-44 |  | INJIWEB-44_TC_05 |  | Download Credential |  | Verify the "Credential download" in incongnito window | 1. Open browser 2. Browse inji home page 3. Select Issuer 4. Select Credential 3. Repeat the steps in incognito | Credentials should be displayed for the selected issuers and Authentication Portal should be opened for authentication | Pass
INJIWEB-44 |  | INJIWEB-44_TC_06 |  | Download Credential |  | Verify that the "Credential donwload" can be selected after search operation | 1. Open browser 2. Browse inji home page 3. Select Issuer 4. Search for a Credential. 5. Click on credential | Credentials should be displayed as per the search criteria Authentication Portal should be opened for authentication | Pass
INJIWEB-44 |  | INJIWEB-44_TC_07 |  | Download Credential |  | Verify credential download page, if there are no credentails associated with the issuer | 1. Open browser 2. Browse inji home page 3. Select Issuer | There should not be any credential download page for empty credentials for an issuer | NA
INJIWEB-44 |  | INJIWEB-44_TC_08 |  | Download Credential |  | Update Crednetials for an issuer in well known file and verify credential list | 1. Update credentials in a well nown file for a particular issuer 2. Restart the necessary services 3. Launch inji home page 4. Select issuer | Updated credential details should be available and can be downloadable | Pass
INJIWEB-45 | [UI] Inji Web: Authentication Portal (eSignet) - Authenticate user credentials | INJIWEB-45_TC_01 |  | Authenticate user credentials |  | Verify all the mandatory fields have * mark Note: if all the fields are mandatory, then * is not mandatory on all the fields | 1. Select credential to download 2. Select OTP based authentication 3. Verify all the mandatory fields have * | All the mandatory fileds should have * symbol If all the fileds are mandatory * not required | Pass
INJIWEB-45 |  | INJIWEB-45_TC_02 |  | Authenticate user credentials |  | Verify Login button enabled if all the mandatory fileds are not entered | 1. Select credential to download 2. Select OTP based authentication 3. do not enter all mandatory fields | Login button should not be enabled untill user enters all the mandatory fields | Pass
INJIWEB-45 |  | INJIWEB-45_TC_03 |  | Authenticate user credentials |  | Verify all the mandatory fields have * mark for KBA authentication Note: if all the fields are mandatory, then * is not mandatory on all the fields | 1. Select credential to download 2. Select KBA based authentication 3. Verify all the mandatory fields have * | All the mandatory fileds should have * symbol | Pass
INJIWEB-45 |  | INJIWEB-45_TC_04 |  | Authenticate user credentials |  | Verify with all valid details | 1. Select credential to download 2. Select KBA based authentication 3. Verify with valid data | Authentication should be passed and Issuer’s “Authentication Portal” page should hold the metadata that will be utilised to generate the pdf certificate. | Pass
INJIWEB-45 |  | INJIWEB-45_TC_05 |  | Authenticate user credentials |  | Verify with invalid details | 1. Select credential to download 2. Select KBA based authentication 3. Verify with invalid data | Authentication should be failed with proper error message: "Login Failed. Wrong details entered. Please enter correct details and login" | Pass
INJIWEB-45 |  | INJIWEB-45_TC_06 |  | Authenticate user credentials |  | Verify with all mandatory fileds | 1. Select credential to download 2. Select KBA based authentication | Login button should be enabled | Pass
INJIWEB-45 |  | INJIWEB-45_TC_07 |  | Authenticate user credentials |  | Verify Login button without entering all the mandatory fileds | 1. Select credential to download 2. Select KBA based authentication 3. Do not enter all mandatory fields | Login button should not be enabled untill user enters all the mandatory fields | Pass
INJIWEB-45 |  | INJIWEB-45_TC_08 |  | Authenticate user credentials |  | Verify proper labels on data field | 1. Select credential to download 2. Select KBA based authentication 3. Verify labels on the fields | Labels should have proper info and with proper alignmnet | Pass
INJIWEB-45 |  | INJIWEB-45_TC_09 |  | Authenticate user credentials |  | Verify text boxes accepting valid data | 1. Select credential to download 2. Select KBA based authentication 3. Verify text boxes accepting data from keyboard | text boxes should have proper labels , aligned properly and should accept data from keyboard | Pass
INJIWEB-45 |  | INJIWEB-45_TC_10 |  | Authenticate user credentials |  | Remove KBA field from config and try to authenticate for existing record | 1. Make sure there is credntial record available 2. Update KBA fields config from esignet-default.properties 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_11 |  | Authenticate user credentials |  | Remove KBA field from config and try to authenticate for new record | 1. Update KBA fields config from esignet-default.properties by removing a field 2. Add a new credential record 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_12 |  | Authenticate user credentials |  | Add KBA field from config and try to authenticate for alredy existing record | 1. Make sure there is credntial record available 2. Update KBA fields config from esignet-default.properties by adding a new field 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_13 |  | Authenticate user credentials |  | Add KBA field from config and try to authenticate for new record | 1. Update KBA fields config from esignet-default.properties by adding a new field 2. Add a new credential record 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_14 |  | Authenticate user credentials |  | Wait for somtime at KBA authentication page and verify for timeout message | 1. Select credetnials and wait for 2 to 3 min 2. Check for timeout message | User should get the timeout message | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-125
INJIWEB-45 |  | INJIWEB-45_TC_15 |  | Authenticate user credentials |  | Verify warning message like "not to refresh/press back button" while downloading the credentials | 1. Select credentials to download 2. Enter valid credentials | User should get the warning message like "not to refresh/press back button" | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-128
INJIWEB-45 |  | INJIWEB-45_TC_16 |  | Authenticate user credentials |  | Add KBA field from config and try to authenticate for alredy existing record | 1. Make sure there is credntial record available 2. Update KBA fields config from esignet-default.properties by adding a new field 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_17 |  | Authenticate user credentials |  | Add KBA field from config and try to authenticate for new record | 1. Update KBA fields config from esignet-default.properties by adding a new field 2. Add a new credential record 3. Try to authenticate | User should able to download the credentials | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-130
INJIWEB-45 |  | INJIWEB-45_TC_18 |  | Authenticate user credentials |  | Wait for somtime at KBA authentication page and verify for timeout message | 1. Select credetnials and wait for 2 to 3 min 2. Check for timeout message | User should get the timeout message | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-125
INJIWEB-45 |  | INJIWEB-45_TC_19 |  | Authenticate user credentials |  | Verify warning message like "not to refresh/press back button" while downloading the credentials | 1. Select credentials to download 2. Enter valid credentials | User should get the warning message like "not to refresh/press back button" | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-128
INJIWEB-47 | PDF is generated and Auto-downloaded to the computer/tablet/smartphone | INJIWEB-47_TC_01 |  | PDF Generation and auto download | 1. The JSON response from the Authentication portal should be available to the Inji Web 2. The user should have already successfully authenticated with the “Authentication Portal” | Verify PDF generation after successful authentication | 1. Select credential to download 2. Authenticate with valid details | PDF should be generated and auto downloaded | Pass
INJIWEB-47 |  | INJIWEB-47_TC_02 |  | PDF Generation and auto download |  | Verify do not “Click Back” button or “ Refresh” the page messages after authentication | 1. Select credential to download 2. Authenticate with valid details | User should get do not “Click Back” button or “ Refresh” the page message while PDF is getting downloaded | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-128
INJIWEB-47 |  | INJIWEB-47_TC_03 |  | PDF Generation and auto download |  | Verify PDF auto download | 1. Select credential to download 2. Authenticate with valid details | PDF should be auto downloaded | Pass
INJIWEB-47 |  | INJIWEB-47_TC_04 |  | PDF Generation and auto download |  | Verify application asking for download path for auto generated PDF | 1. Select credential to download 2. Authenticate with valid details | Verify application asking for download path to save PDF file | Pass
INJIWEB-47 |  | INJIWEB-47_TC_05 |  | PDF Generation and auto download |  | Open the donwloaded PDF | 1. Select credential to download 2. Authenticate with valid details 3. Open the downloaded PDF | PDF should be readble and should contain the details as per configuration | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-131
INJIWEB-47 |  | INJIWEB-47_TC_06 |  | PDF Generation and auto download |  | Verify Key Fields in the PDF certificate | 1. Select credential to download 2. Authenticate with valid details 3. Open the downloaded PDF 4. Verify fields in PDF file | PDF should be readble and should contain the details as per configuration.. 1. Certificate name 2. Name of the Holder of the certificate 3. Name of the institution issuing this certificate 4. Dummy QR code 5. All other details as defined in the config file 6. Logo of the credential issuer | Fail |  |  |  | https://mosip.atlassian.net/browse/INJIWEB-131
INJIWEB-48 | [UI] Inji Web - Success/Failure notifier after downloading the VC PDF | INJIWEB-48_TC_01 |  | Success/Failure notifier after downloading the VC PDF | 1. A credential was immediately earlier/earlier downloaded in the same tab 2. The Inji Download credential Page or its latest updated version should be available in the appropriate URL (<URL link to be updated here>) | Verify success message after VC downloaded | 1. Select credential to download 2. Authenticate with valid details | Application should display success message after VC download | Pass
INJIWEB-48 |  | INJIWEB-48_TC_02 |  | Success/Failure notifier after downloading the VC PDF |  | Verify Failure message if VC download failed | 1. Select credential to download 2. Authenticate with valid details 3.Try to fail VC download | Application should display failure message if failed download VC | NA
INJIWEB-48 |  | INJIWEB-48_TC_03 |  | Success/Failure notifier after downloading the VC PDF |  | Verify Back button on the inji downloaded page | 1. Select credential to download 2. Authenticate with valid details | Application should display back button on the same tab after successful VC download | Pass
INJIWEB-48 |  | INJIWEB-48_TC_04 |  | Success/Failure notifier after downloading the VC PDF |  | Verify back button functionality after download operatation | 1. Select credential to download 2. Authenticate with valid details 3 Verify back button after VC download | All the credentials should displayed | Pass
INJIWEB-48 |  | INJIWEB-48_TC_05 |  | Success/Failure notifier after downloading the VC PDF |  | Verify error message if internet bandwidth is slow and unable to download PDF | 1. Select credential to download 2. Authenticate with valid details 3 Verify VC download on low bandwidth | Proper error message should be displayed if the internet bandwidth is slow, while downloading VC | Pass
INJIWEB-48 |  | INJIWEB-48_TC_06 |  | Success/Failure notifier after downloading the VC PDF |  | Verify error message if unable to generate PDF for particular credential | 1. Select credential to download 2. Authenticate with valid details | Proper error message should be displayed if the credentails generation failed for a particular credential | NA
INJIWEB-48 |  | INJIWEB-48_TC_07 |  | Success/Failure notifier after downloading the VC PDF |  | Verify error message if endpoint failed to reach the data provider even for successful authentication | 1. Select credential to download 2. Authenticate with valid details | Proper error message if failed to reach the particular endpoint | NA
INJIWEB-48 |  | INJIWEB-48_TC_08 |  | Success/Failure notifier after downloading the VC PDF |  | Verify download endpoint timed out if there is issue in upstream service | 1. Select credential to download 2. Authenticate with valid details | Proper error message should be displayed if timeout happened to reach a particular upstrean end point | NA
INJIWEB-49 | [BE]: API to retrieve issuers list | INJIWEB-49_TC_01 | API | Retrieve issuers list | 1. Mimoto to be onboarded as an OIDC client in the environment. 2. mimoto-issuers config json should have all the issuers listed with the auth end point. | Get the list of issuers from the issuers end point | 1. Execute GET method to get all the issuers list End Point : https://{url}/residentmobileapp /issuers | All the issuers should be retrived with the GET request | Pass
INJIWEB-49 |  | INJIWEB-49_TC_02 |  | Retrieve issuers list |  | Update the issuers list in mimoto-issuers config json and execute GET issuers | 1. Update the issuers in mimoto-issuers config json 2.Restart the necessary services 3. Execute GET method to get all the issuers list | All the issuers / Updated issuers should be retrived with the GET request | Pass
INJIWEB-49 |  | INJIWEB-49_TC_04 |  | Retrieve issuers list |  | Verify the error message if endpoint is unable to retrieve data within the predefined time. | 1. Execute GET method to get all the issuers list 2 Make sure the time taken for response is more | End point should handle the delay in response and hang/crash should not be happen | Pass
INJIWEB-49 |  | INJIWEB-49_TC_05 |  | Retrieve issuers list |  | Verify error messages and logging messages are appropriate with the API | 1. Execute GET method to get all the issuers list 2 Verify all error messages/logging messages for failure cases | The response should include an error code and message for logging purposes, as well as an appropriate status code. | Pass
INJIWEB-49 |  | INJIWEB-49_TC_06 |  | Retrieve issuers list |  | Verify GET method o/p if the issuers configuration is empty | 1. Execute GET method to get the issuers list | GET methos should return the status code as 200 but the response should have a message that there are no list of issuers. | Pass
INJIWEB-49 |  | INJIWEB-49_TC_07 |  | Retrieve issuers list |  | Verify error messages if the end point unbale to retreive the data | 1. Execute GET method to get the issuers list | Proper error message should be displayed, if the end point not able to retrieve the data | Pass
INJIWEB-50 | [BE]: API to retrieve credential types | INJIWEB-50_TC_01 | API | Retrieve credential types | 1. Mimoto to be onboarded as an OIDC client in the environment. 2. mimoto-issuers config json should have all the issuers listed with the auth end point. 3. mimoto-issuers config json should have the well-known endpoint configured for the issuer. | Get the list credential types for an issuer | 2. Execute GET method to get all the credential types of a particular issuer from the credential end point(Pass the issuer as path parameter) End Point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentialTypes | All the all the credential types of a particular issuer should be retrieved with status code 200. | Pass
INJIWEB-50 |  | INJIWEB-50_TC_02 |  | Retrieve credential types |  | try to Get the list credential types for an issuer with invalid credential | with invalid details | Authentication should fail with 400 error. | Pass
INJIWEB-50 |  | INJIWEB-50_TC_03 |  | Retrieve credential types |  | Get the list credential types for diff issuer | 2. Execute GET method to get all the credential types of a particular issuer from the credential end point(Pass the issuer as path parameter) | All the all the credential types of a particular issuer should be retrieved with status code 200. | Pass
INJIWEB-50 |  | INJIWEB-50_TC_04 |  | Retrieve credential types |  | Update credentials for a particular issuer and Execute Get request for credential types | 1. Update the credential details for a particular issuer 2. Restart the neccessary services 3. Authenticate with Mimoto client details 4. Execute GET method to get all the credential types of a particular issuer from the credential end point(Pass the issuer as path parameter) | All the all updated details for a particular issuer should be retrieved with status code 200. | Pass
INJIWEB-50 |  | INJIWEB-50_TC_05 |  | Retrieve credential types |  | Verify timeout response for GET request on credetial type end point | 2. Execute GET method to get all the credential types of a particular issuer from the credential end point(Pass the issuer as path parameter) 3. Make sure request failed to retreive the data in predefined time frame | End point should handle the delay in response and hang/crash should not be happen | Pass
INJIWEB-50 |  | INJIWEB-50_TC_06 |  | Retrieve credential types |  | Verify error messages and logging messages are appropriate with the API | 2. Make sure to fail GET request method while retrieving credential types of a particular issuer from the credential end point | The response should include an error code and message for logging purposes, as well as an appropriate status code. | Pass
INJIWEB-50 |  | INJIWEB-50_TC_07 |  | Retrieve credential types |  | Verify the response when API request failed on particular end point | 2. Execute GET method to get all the credential types of a particular issuer from the credential end point and Pass the invalid issuer as path parameter | Appropriate error message should be thrown by the end point | Pass
INJIWEB-50 |  | INJIWEB-50_TC_08 |  | Retrieve credential types |  | Verify GET method o/p if the credential type configuration is empty | 2. Execute GET method to get all the credential types of a particular issuer from the credential end point and Pass the valid issuer as path parameter | API should return status code as 200 but the response should have a message that there are no list of credential types. | Pass
INJIWEB-51 | [BE]: API to download VC as PDF | INJIWEB-51_TC_01 | API | Download VC as PDF | 1. Mimoto to be onboarded as an OIDC client in the environment. 2. mimoto-issuers config json should have all the issuers listed with the auth end point. 3 mimoto-issuers config json should have the well-known endpoint configured for the issuer. 4 OTP/KBA authentication to be integrated. | Execute GET request on download VC end point | 1. Authenticate at mimoto get-token endpoint 2. Execute GET method on end point End Point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentials/{credentialType}/download | VC should be downloaded as PDF | NA
INJIWEB-51 |  | INJIWEB-51_TC_02 |  | Download VC as PDF |  | Execute GET request on download VC end point with invalid token | 1. Authenticate at mimoto get-token endpoint 2. Execute GET method on end point with invalid token say expired or invalid details End point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentials/{credentialType}/downlo | VC download should fail with Error: 401 authentication failure message | NA
INJIWEB-51 |  | INJIWEB-51_TC_03 |  | Download VC as PDF |  | Verify timeout response for GET request on download end point | 1. Authenticate at mimoto get-token endpoint 2. Execute GET method on end point with valid token 3. Make sure that the resonse is slow from the end point End point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentials/{credentialType}/downlo | End point should handle the delay in response and hang/crash should not be happen | NA
INJIWEB-51 |  | INJIWEB-51_TC_04 |  | Download VC as PDF |  | Verify error messages and logging messages are appropriate with the API | 1. Authenticate at mimoto get-token endpoint 2. Execute GET method on end point with invalid details End point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentials/{credentialType}/downlo | Appropriate error message and code should be thrown by the API | NA
INJIWEB-51 |  | INJIWEB-51_TC_05 |  | Download VC as PDF |  | Verify error message if the end point unable to send PDF file | 1. Authenticate at mimoto get-token endpoint 2. Execute GET method on end point with invalid credentials details End point: https://api.mosip.io/residentmobileapp /issuers/{issuer-id}/credentials/{credentialType}/downlo | Appropriate error message and code should be thrown by the API | NA
|  | INJIWEB-291 |  | Multi languages support |  |  | Open inji web portal Select an issuer Select Credential type Authenticate with valid details Open the downloaded VC card Also, try to translate the page in before to another language and perform the steps from 1 to 5 | All the messages should be in the language that we selected. | Fail |  |  |  | INJIWEB-291
|  | INJIWEB-290 |  | QR code on VC card |  |  | Open inji web portal Select an issuer Select Credntial type Authenticate with valid details Open the downloaded VC card Verify the QR code using QR scanner | QR code should provide the details related to VC | Fail |  |  |  | INJIWEB-290
|  | INJIWEB-288 |  | Cross browser verification |  |  | Open inji web portal Select an issuer Select Credntial type | Date format should be the same in all the browsers. | Fail |  |  |  | INJIWEB-288
|  | INJIWEB-243 |  | Search bar functionality |  |  | Open the inji web portal Observe the search bar Select the issuer Observe search bar | Search bar should not contain dropdown buttons | Fail |  |  |  | INJIWEB-243
|  | INJIWEB-180 |  | Error message when the website is down |  |  | Make the inji-web service down Open the inji web site | 503 gateway error message should be displayed | Fail |  |  |  | INJIWEB-180
|  | INJIWEB-132 |  | Data in VC(PDF) Alignment |  |  | Launch inji web portal Select issuer Select credential Enter Valid credentials Download VC and open PDF file | Data alignment in VC is not proper | Fail |  |  |  | INJIWEB-132
|  | INJIWEB-128 |  |  |  |  | Launch inji web portal Select issuer Select credential Enter Valid credentials | After entering the data, user should get "do not Click Back” button or “ Refresh” the page message | Fail |  |  |  | INJIWEB-128
|  | INJIWEB-122 |  | Login fail error message |  |  | Launch inji web portal Select issuer Select credential Enter invalid details and click on login | Error message is not user readble format | Fail |  |  |  | INJIWEB-122

## Known issues
Bug id | Issue | Severity
INJIWEB-394 | Expiry date is coming in TZ format instead of human readable | Major
INJIWEB-291 | Inji-web: Multi languages support is not working at Authentication window | Major
INJIWEB-290 | Inji-web: QR code is not working on VC card | Major
INJIWEB-288 | Inji-web: For Safari broswer calender at authenticatication page considering dd/mm/yyyy format But in other browsers mm/dd/yyyy format | Minor
INJIWEB-243 | Inji-web: Observed drop down box in search bar at issuer selection page as well as at credential download pages | Minor
INJIWEB-180 | Inji-web: :Not getting proper error message when the website is down | Minor
INJIWEB-132 | Inji-web: Data in VC(PDF) are not properly aligned | Major
INJIWEB-131 | Inji-web: attributes are missing compared to the VC on inji mobile | Critical
INJIWEB-130 | Inji-web: we are not able to download VC if we remove an atribute from authenticator | Major
INJIWEB-128 | Inji-web: After entering the data, user is not getting "do not Click Backâ€ button or â€œ Refreshâ€ the page message | Major
INJIWEB-125 | Inji-web: Getting invalid credentials error message for valid data, when we leave authentication page idle for sometime | Major
INJIWEB-122 | Inji-web: Login failed error message should be in user readable format | Minor

## Feature Health
Feature list | INJI Web
Inji Web Home page | Pass
Issuer selection in the “Home Page” | Pass
Authenticate user credentials | Pass
PDF Generation and auto download | Pass
Download Credential | Pass
Success/Failure notifier after downloading VC | Pass
Download VC as PDF | Pass
Retrieve issuers list | Pass
Retrieve credential types | Pass
Search bar functionality | Pass

## NL Android test cases (hidden)
TestCase_No | Feature | Scenario | Result

## NL ios test cases (hidden)
TestCase_No | Feature | Scenario | Result

## Bug tracker - Android (hidden)
Bug tracker
TICKET# | Bug Title | Status | Severity | Notes
https://github.com/mosip/inji/issues/135 | Unable to download credential displayed invalid input Parameter - mobileNumber | OPEN | Blocker
https://github.com/mosip/inji/issues/134 | Unable to download credential displayed UIN not available in Database | OPEN | Blocker
https://github.com/mosip/inji/issues/137 | mpartner-default-mobile partner details is missing in kernel default properties | OPEN | Blocker
https://github.com/mosip/inji/issues/157 | Get UIN/VID text box has a not working question mark | closed
https://github.com/mosip/inji/issues/137 | mpartner-default-mobile partner details is missing in kernel default properties | closed
https://github.com/mosip/inji/issues/135 | Unable to download credential displayed invalid input Parameter - mobileNumber | closed
https://github.com/mosip/inji/issues/178 | Unable to download VC | OPEN | Blocker
https://github.com/mosip/inji/issues/159 | To turn on the bluetooth "Go to setting" button is not working | OPEN
https://github.com/mosip/inji/issues/158 | Get UIN/VID text box has a question mark | OPEN
https://github.com/mosip/inji/issues/155 | VC's border is not round edged properly | OPEN
https://github.com/mosip/inji/issues/153 | Reason for sharing getting over layed out of the VC details | OPEN
https://github.com/mosip/inji/issues/148 | Edit tag option making changes in UIN values in the home screen | OPEN
https://github.com/mosip/inji/issues/147 | full name atribute taking the place of ID type in VC | OPEN
https://github.com/mosip/inji/issues/146 | ID type feild is empty in the downloaded VC | OPEN
https://github.com/mosip/inji/issues/143 | VC address values getting overlaped | OPEN
https://github.com/mosip/inji/issues/142 | MOSIP logo trimed in VC card | OPEN
https://github.com/mosip/inji/issues/140 | VC stuck at loading state in Mobile ID app | OPEN
https://github.com/mosip/inji/issues/196 | Unable to download VC with arabic language UIN | OPEN | Blocker
https://github.com/mosip/inji/issues/197 | RTL is not handled in inji app | OPEN
https://github.com/mosip/inji/issues/199 | The full name attribute is missing in the VC detailed view | OPEN
https://github.com/mosip/inji/issues/200 | VC detailed layout is not ocupying the spaces properly | OPEN
https://github.com/mosip/inji/issues/201 | The android app is not fully capable with diffrent language filters | OPEN
https://github.com/mosip/inji/issues/202 | When the VC card is downloading it has two id type's attribute | OPEN
https://github.com/mosip/inji/issues/228 | Mobile-id mail's where been looped | Open

## Bug tracker - ios (hidden)
Bug tracker
JIRA # | Bug Title | Status | Notes | new apk
https://github.com/mosip/inji/issues/191 | Application ID text box has a question mark. | Open
https://github.com/mosip/inji/issues/193 | VC's border is not round edged properly | Open
https://github.com/mosip/inji/issues/195 | Renaming VC replacing UIN number in the home screen | Open
https://github.com/mosip/inji/issues/203 | RTL is not handled in inji app | Open
https://github.com/mosip/inji/issues/206 | MOSIP logo trimed in VC card | Open
https://github.com/mosip/inji/issues/208 | Unable to download VC with the UIN which is created in Arabic language. | Open
https://github.com/mosip/inji/issues/209 | Unable to download credential with infant's UIN. | Open
https://github.com/mosip/inji/issues/210 | Message should be revised in sharing device while waiting for receiver to accept VC | Open
https://github.com/mosip/inji/issues/211 | VC is not in card format in sharing device. | Open
https://github.com/mosip/inji/issues/212 | Radio button should be removed if device contain single VC while sharing. | Open
https://github.com/mosip/inji/issues/213 | While Downloading VC field Name is displayed as idtype instead of UIN. | Open
https://github.com/mosip/inji/issues/214 | Message popup in sharing device is still retained even after successful VC share. | Open
https://github.com/mosip/inji/issues/217 | The ADD ID button is getting stacked down by the VC card | Open
https://github.com/mosip/inji/issues/218 | No Message to User for asking to enable the internet while sharing VC between devices. | Open
https://github.com/mosip/inji/issues/219 | Even though requesting credential with VID still we see UIN detials in the app | Open
https://github.com/mosip/inji/issues/221 | Unable to see the version of the app in profile icon due to smaller screen length | Open
https://github.com/mosip/inji/issues/222 | Rejection of VC request by sharing device should be notified to requesting device. | Open
https://github.com/mosip/inji/issues/223 | In inji app still labels and button remained in english even after language switch | Open
https://github.com/mosip/inji/issues/225 | Name and Device reference number fields are missing in sharing device | Open
https://github.com/mosip/inji/issues/231 | Inji app is not prompting the user to grant location access | Open
https://github.com/mosip/inji/issues/232 | VC detailed layout is not ocupying the spaces properly | Open
https://github.com/mosip/inji/issues/228 | Mobile-id mail's where been looped | Open
https://github.com/mosip/inji/issues/259 | Error message should be revised when biometrics is not enrolled in device settings page but still resident use biometric unlock | Open
https://github.com/mosip/inji/issues/262 | Sharing device is not displaying success pop up message after sharing a VC | Open
https://github.com/mosip/inji/issues/302 | A successful face match is not displaying the message in sharing device. | Open

## Release-bugs (hidden)
Bug id | Bug title | ios | android | assignee | status | remarks
293 | Camera is not launched in verifier's phone even after giving the consent from Resident's phone. | yes | yes | anushree | closed
291 | otp generation is failing with the error "while generating otp error is occured" | yes | yes | anushree/santhosh | closed
276 | Inji app crashing while sharing | no | yes | santhosh | closed |  | closed
252 | Change the static message on Sharing and Receiving device during sharing ID | yes | yes | anushree/santhosh | Verified and added comment |  | closed , Android | Added my comment waiting for reply.
231 | Inji app is not prompting the user to grant location access | yes | no | anushree | closed
226 | Name and Device reference number fields are missing in sharing device and also on requesting device | no | yes | santhosh | closed |  | closed
225 | Name and Device reference number fields are missing in sharing device and also on requesting device | yes | no | anushree | re-opened |  | Added my comments
223 | In inji app still labels and button remained in english even after language switch | yes | no | anushree | re-opened |  | reopen
220 | Even though requesting credential with VID still we see UIN detials in the app | no | yes | santhosh | Assigned for testing | story not provided yet
219 | Even though requesting credential with VID still we see UIN detials in the app | yes | no | anushree | VID support not available
217 | The ADD ID button is getting stacked down by the VC card | yes | no | anushree | closed |  | closed
216 | The ADD ID getting stacked down by the VC card | no | yes | santhosh | closed
215 | Mobile id API credentials are not moving to printing state |  |  | santhosh | closed
213 | While Downloading VC field Name is displayed as idtype instead of UIN. | yes | no | anushree | closed
212 | Radio button should be removed if device contain single VC while sharing. | yes | no | anushree | closed
209 | Unable to download credential with infant's UIN | yes | no | anushree | Assigned for testing
205 | Full name attribute is missing in detail view screen of VC | yes | no | anushree | closed
203 | RTL is not handled in inji app | yes | no | anushree | re-opened |  | reopen
199 | The full name attribute is missing in the VC detailed view | no | yes | santhosh | closed
197 | RTL is not handled in inji app | no | yes | santhosh | re-opened | check in this build
196 | Unable to download VC with arabic language UIN | no | yes | santhosh | re-opened
195 | Renaming VC replacing UIN number in the home screen | yes | no | anushree | closed
191 | Application ID text box has a question mark. | yes | no | anushree | re-opened
187 | Unable to delete the numbers in the textbox in AID screen | yes | no | anushree | closed
158 | Get UIN/VID text box has a question mark | no | yes | santhosh | re-opened
156 | When a requesting device cancels a sharing request device details are still displayed in the sharing device |  |  | santhosh | closed
155 | VC's border is not round edged properly | no | yes | santhosh | re-opened
154 | Connection is not established even after scanning qr code | yes | no | anushree | closed
140 | VC stuck at loading state in Mobile ID app | no | yes | santhosh | closed |  | closed
114 | Mobile id - can't change the field from uin to vid while generating id | yes | yes | anushree/santhosh | closed
112 | App is continuously flickering when app is open but phone kept idle for some duration | no | yes | santhosh | re-opened |  | Added my comments
111 | mobile id - Template exceptionServiceError occurring while downloading VC | no | yes | santhosh | re-opened
110 | mobile id - 2 buttons are displayed in APK home page | no | yes | santhosh | re-opened |  | reopen
94 | When Residents request VC with VID the UIN label should be changed to VID | no | yes | santhosh | story not provided yet
79 | "network request failed" message is still showing after the network is connected when we try to add id and when otp is provided | no | yes | santhosh | closed
261 | iOS: app should detect if the user’s biometrics changes in the device settings page | yes | no | anushree | Not assigned for testing
260 | Error message should be revised when biometrics is not enrolled in device settings page but still resident use biometric unlock | no | yes | santhosh | closed
259 | Error message should be revised when biometrics is not enrolled in device settings page but still resident use biometric unlock | yes | no | anushree | closed |  | closed
210 | Message should be revised in sharing device while waiting for receiver to accept VC | yes | no | anushree | re-opened
90 | Mobile app session should get expire ,if the app is opened longer time | no | yes | santhosh | Check if we can verify this bug
87 | The error message "connection interrupted" should be revised to more user friendly message | no | yes | santhosh | Check if we can verify this bug
201 | The inji app is not supported with multi language | no | yes | santhosh | re-opened
280 | App crashed after viewing a Received ID | yes | yes | anushree/santhosh | Verified and added comment | closable form android
214 | Message popup in sharing device is still retained even after successful VC share | yes | yes | anushree/santhosh | closed
249 | When Cancel button is clicked during sharing, no prompt is displayed on the receiving device that the sharing was cancelled | yes | yes | anushree/santhosh | re-opened
250 | No prompt is displayed on the Sharing device when Cancel is clicked on the Receiving device during sharing | yes | yes | anushree/santhosh | re-opened
214 | Message popup in sharing device is still retained even after successful VC share. | yes | no | anushree | closed
291 | otp generation is failing with the error "while generating otp error is occured | yes | yes | anushree/santhosh | closed
324 | The consent was automatically selected while sharing | no | yes | santhosh | closed
325 | The consent was automatically selected in the second attempt of sharing | yes | no | anushree | Closed
330 | iOS : Audit should be logged for rejection of incoming VC by Receiver. | yes | no | anushree | Closed
351 | Android - Able to get inside app without adding pin | no | yes | santhosh | closed
373 | iOS - Able to unlock the inji app just with biometrics without passcode as a fallback | yes | no | anushree | Closed
201 | The inji app is not supported with multi language | yes | yes | santhosh | Assigned for testing
155 | VC's border is not round edged properly | no | yes | santhosh | Assigned for testing | comment added
211 | VC is not in card format in sharing device. | yes | no | anushree | Closed
232 | VC detailed layout is not ocupying the spaces properly | yes | yes | anushree/santhosh | re-opened | Re-opened from iOS | comment added, closable from android side
383 | Android - spelling mistake in the tips/user guide note | yes | yes | anushree/santhosh | Closed |  | comment added, closable from android side
94 | When Residents request VC with VID the UIN label should be changed to VID | no | yes | santhosh | VID support not available
200 | VC detailed layout is not ocupying the spaces properly | no | yes | santhosh | closed
202 | When the VC card is downloading it has two id type's attribute | no | yes | santhosh | closed

## BLE testing-sharing flow (hidden)
Device names | verifier | wallet | BLE sanity status | Status with jan 30th build | remarks | Status with Feb 8th build |  | app size after installation | app size after 1 vc download | app size after 4 vc download
redmi 6A, redmi 7A | Android 9 BLE 4.2 | Android 10 BLE 4.2 | normal sharing | pass |  | pass
redmi 6A, redmi 7A | Android 9 BLE 4.3 | Android 10 BLE 4.3 | face auth on resident's phone | pass |  | pass
redmi 6A, redmi 7A | Android 9 BLE 4.4 | Android 10 BLE 4.4 | face auth on receiver's phone | Pass |  | pass
Redmi 6A, Redmi note 10 lite | Android 9 BLE 4.2 | Android 10 BLE 5.0 | normal sharing | fail | second attempt not working | pass
Redmi 6A, Redmi note 10 lite | Android 9 BLE 4.2 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass
Redmi 6A, Redmi note 10 lite | Android 9 BLE 4.2 | Android 10 BLE 5.0 | face auth on receiver's phone | pass |  | pass
redmi 7A, redmi note 10 lite | Android 10 BLE 4.2 | Android 10 BLE 5.0 | normal sharing | pass |  | pass
redmi 7A, redmi note 10 lite | Android 10 BLE 4.2 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass
redmi 7A, redmi note 10 lite | Android 10 BLE 4.2 | Android 10 BLE 5.0 | face auth on receiver's phone | pass |  | pass |  |  |  |  | device name | verifier | wallet
[11 empty] | redmi 6A, redmi 7A | Android 9 BLE 4.2 | Android 10 BLE 4.2
redmi 7A, Vivo Y73 | Android 10 BLE 4.2 | Android 12 BLE 5.0 | normal sharing | Pass |  | pass |  |  |  |  | Redmi 6A, Redmi note 10 lite | Android 9 BLE 4.2 | Android 10 BLE 5.0
redmi 7A, Vivo Y74 | Android 10 BLE 4.2 | Android 12 BLE 5.0 | face auth on resident's phone | pass |  | pass |  |  |  |  | redmi 7A, redmi note 10 lite | Android 10 BLE 4.2 | Android 10 BLE 5.0
redmi 7A, Vivo Y75 | Android 10 BLE 4.2 | Android 12 BLE 5.0 | face auth on receiver's phone | Pass |  | pass |  |  |  |  | redmi 7A, Vivo Y73 | Android 10 BLE 4.2 | Android 12 BLE 5.0
[11 empty] | redmi note 10 lite, samsung galaxy A03 core | Android 10 BLE 5.0 | Android 11 BLE 4.2
redmi note 10 lite, samsung galaxy A03 core | Android 10 BLE 5.0 | Android 11 BLE 4.2 | normal sharing | pass |  | pass |  |  |  |  | samsung galaxy A03 core, redmi note 10 lite | Android 11 BLE 4.2 | Android 10 BLE 5.0
redmi note 10 lite, samsung galaxy A03 core | Android 10 BLE 5.0 | Android 11 BLE 4.2 | face auth on resident's phone | pass |  | pass |  |  |  |  | redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0
redmi note 10 lite, samsung galaxy A03 core | Android 10 BLE 5.0 | Android 11 BLE 4.2 | face auth on receiver's phone | pass |  | pass |  |  |  |  | redmi K20 pro, redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0
[11 empty] | redmi note 10 lite, Vivo Y73 | Android 10 BLE 5.0 | Android 12 BLE 5.0
samsung galaxy A03 core, redmi note 10 lite | Android 11 BLE 4.2 | Android 10 BLE 5.0 | normal sharing | pass |  | pass |  |  |  |  | Redmi 7A, Redmi 6A | Android 10 BLE 4.2 | Android 9 BLE 4.2
samsung galaxy A03 core, redmi note 10 lite | Android 11 BLE 4.2 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass |  |  |  |  | redmi note 10 lite, redmi 7A | Android 10 BLE 4.2 | Android 9 BLE 4.2
samsung galaxy A03 core, redmi note 10 lite | Android 11 BLE 4.2 | Android 10 BLE 5.0 | face auth on receiver's phone | pass |  | pass |  |  |  |  | redmi note 10 lite, redmi 6A | Android 10 BLE 5.0 | Android 9 BLE 4.2
[11 empty] | redmi K20 pro, Redmi 7A | Android 11 BLE 5.0 | Android 10 BLE 4.2
redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | normal sharing | pass |  | pass |  |  |  |  | Vivo Y73, Redmi 7A | Android 12 BLE 5.0 | Android 10 BLE 4.2
redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | face auth on resident's phone | pass |  | pass |  |  |  |  | Vivo Y73, Redmi Note 10 lite | Android 12 BLE 5.0 | Android 10 BLE 5.0
redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | face auth on receiver's phone | pass |  | pass |  |  |  |  | Redmi K20 pro, Redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0
[11 empty] | Redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0
redmi K20 pro, redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | normal sharing | pass |  | pass
redmi K20 pro, redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass
redmi K20 pro, redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | face auth on receiver's phone | pass |  | pass
redmi note 10 lite, Vivo Y73 | Android 10 BLE 5.0 | Android 12 BLE 5.0 | normal sharing | fail | second attempt not working | pass
redmi note 10 lite, Vivo Y73 | Android 10 BLE 5.0 | Android 12 BLE 5.0 | face auth on resident's phone | Pass |  | pass
redmi note 10 lite, Vivo Y73 | Android 10 BLE 5.0 | Android 12 BLE 5.0 | face auth on receiver's phone | Pass |  | pass
Redmi 7A, Redmi 6A | Android 10 BLE 4.2 | Android 9 BLE 4.2 | normal sharing | pass |  | pass
Redmi 7A, Redmi 6A | Android 10 BLE 4.2 | Android 9 BLE 4.2 | face auth on resident's phone | pass |  | pass
Redmi 7A, Redmi 6A | Android 10 BLE 4.2 | Android 9 BLE 4.2 | face auth on receiver's phone | pass |  | pass
redmi note 10 lite, redmi 7A | Android 10 BLE 5.0 | Android 10 BLE 4.2 | normal sharing | pass |  | pass
redmi note 10 lite, redmi 7A | Android 10 BLE 5.0 | Android 10 BLE 4.2 | face auth on resident's phone | pass |  | pass
redmi note 10 lite, redmi 7A | Android 10 BLE 5.0 | Android 10 BLE 4.2 | face auth on receiver's phone | pass |  | pass
redmi note 10 lite, redmi 6A | Android 10 BLE 5.0 | Android 9 BLE 4.2 | normal sharing | fail | second attempt not working | pass
redmi note 10 lite, redmi 6A | Android 10 BLE 5.0 | Android 9 BLE 4.2 | face auth on resident's phone | pass |  | pass
redmi note 10 lite, redmi 6A | Android 10 BLE 5.0 | Android 9 BLE 4.2 | face auth on receiver's phone | pass |  | pass
redmi K20 pro, Redmi 7A | Android 11 BLE 5.0 | Android 10 BLE 4.2 | normal sharing | pass |  | pass
redmi K20 pro, Redmi 7A | Android 11 BLE 5.0 | Android 10 BLE 4.2 | face auth on resident's phone | pass |  | pass
redmi K20 pro, Redmi 7A | Android 11 BLE 5.0 | Android 10 BLE 4.2 | face auth on receiver's phone | pass |  | pass
Vivo Y73, Redmi 7A | Android 12 BLE 5.0 | Android 10 BLE 4.2 | normal sharing | fail | second attempt not working | pass
Vivo Y73, Redmi 7A | Android 12 BLE 5.0 | Android 10 BLE 4.2 | face auth on resident's phone | pass |  | pass
Vivo Y73, Redmi 7A | Android 12 BLE 5.0 | Android 10 BLE 4.2 | face auth on receiver's phone | pass |  | pass
Vivo Y73, Redmi Note 10 lite | Android 12 BLE 5.0 | Android 10 BLE 5.0 | normal sharing | fail | app crashing intermittently while connecting | pass
Vivo Y73, Redmi Note 10 lite | Android 12 BLE 5.0 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass
Vivo Y73, Redmi Note 10 lite | Android 12 BLE 5.0 | Android 10 BLE 5.0 | face auth on receiver's phone | pass |  | pass
Vivo Y73, Redmi K20 pro | Android 12 BLE 5.0 | Android 11 BLE 5.0 | normal sharing | fail | app crashing intermittently while connecting | pass
Vivo Y73, Redmi K20 pro | Android 12 BLE 5.0 | Android 11 BLE 5.0 | face auth on resident's phone | fail |  | pass
Vivo Y73, Redmi K20 pro | Android 12 BLE 5.0 | Android 11 BLE 5.0 | face auth on receiver's phone | pass |  | pass
Redmi K20 pro, vivo Y73 | Android 11 BLE 5.0 | Android 12 BLE 5.0 | normal sharing | fail | device not connecting in this specific roles | blocked
Redmi K20 pro, vivo Y73 | Android 11 BLE 5.0 | Android 12 BLE 5.0 | face auth on resident's phone | blocked |  | blocked
Redmi K20 pro, vivo Y73 | Android 11 BLE 5.0 | Android 12 BLE 5.0 | face auth on receiver's phone | blocked |  | blocked
Redmi K20 pro, Redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | normal sharing | pass |  | pass
Redmi K20 pro, Redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | face auth on resident's phone | pass |  | pass
Redmi K20 pro, Redmi note 10 lite | Android 11 BLE 5.0 | Android 10 BLE 5.0 | face auth on receiver's phone | fail | Face auth failed | pass
Redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | normal sharing | pass |  | pass
Redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | face auth on resident's phone | fail | Face auth failed | pass
Redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0 | Android 11 BLE 5.0 | face auth on receiver's phone | pass |  | pass
vivo y73 , iphone 11 | Android 12 BLE 5.0 | iPhone 15 BLE 5.0 | normal sharing | fail | app crashing | intermittently sharing is not working | ios as wallet
vivo y73 , iphone 11 | Android 12 BLE 5.0 | iPhone 15 BLE 5.0 | face auth on resident's phone | fail | app crashing | intermittently sharing is not working | android as verifier
vivo y73 , iphone 11 | Android 12 BLE 5.0 | iPhone 15 BLE 5.0 | face auth on receiver's phone | fail | app crashing | intermittently sharing is not working
k20 pro , iphone 8 | Android 11 BLE 5.0 | iphone 16 BLE 5.0 | normal sharing | Blocked |  | intermittently sharing is not working
k20 pro , iphone 8 | Android 11 BLE 5.0 | iphone 16 BLE 5.0 | face auth on resident's phone | Blocked |  | intermittently sharing is not working
k20 pro , iphone 8 | Android 11 BLE 5.0 | iphone 16 BLE 5.0 | face auth on receiver's phone | Blocked |  | intermittently sharing is not working
k20 pro , iphone 11 | Android 11 BLE 5.0 | iPhone 15 BLE 5.0 | normal sharing | intermittently |  | intermittently sharing is not working
k20 pro , iphone 11 | Android 11 BLE 5.0 | iPhone 15 BLE 5.0 | face auth on resident's phone | intermittently |  | intermittently sharing is not working
k20 pro , iphone 11 | Android 11 BLE 5.0 | iPhone 15 BLE 5.0 | face auth on receiver's phone | intermittently |  | intermittently sharing is not working
redmi 7a , iphone 8 | Android 10 BLE 4.2 | iphone 16 BLE 5.0 | normal sharing |  |  | Blocked
redmi 7a , iphone 8 | Android 10 BLE 4.2 | iphone 16 BLE 5.0 | face auth on resident's phone |  |  | Blocked
redmi 7a , iphone 8 | Android 10 BLE 4.2 | iphone 16 BLE 5.0 | face auth on receiver's phone |  |  | Blocked
redmi 6a, iphone 7 | Android 9 BLE 4.2 | iphone 15.6 BLE 4.2 | normal sharing |  |  | Blocked
redmi 6a, iphone 7 | Android 9 BLE 4.2 | iphone 15.6 BLE 4.2 | face auth on resident's phone |  |  | Blocked
redmi 6a, iphone 7 | Android 9 BLE 4.2 | iphone 15.6 BLE 4.2 | face auth on receiver's phone |  |  | Blocked
redmi 7a , iphone 7 | Android 10 BLE 4.2 | iphone 15.6 BLE 4.2 | normal sharing | Blocked
redmi 7a , iphone 7 | Android 10 BLE 4.2 | iphone 15.6 BLE 4.2 | face auth on resident's phone | Blocked
redmi 7a , iphone 7 | Android 10 BLE 4.2 | iphone 15.6 BLE 4.2 | face auth on receiver's phone | Blocked

## BLE testing-independant feature (hidden)
| Sanity | Status
Android 10 BLE 4.2 | Passcode unlock | Pass
| biometric unlock | N/A
| downloading VC with VID | Pass
| wallet binding | Pass
| qrcode login | Pass
Android 12 BLE 5.0 | Passcode unlock | Pass
| biometric unlock | pass
| downloading VC with VID | pass
| wallet binding | Pass
| qrcode login | Pass
Android 9 BLE 4.2 | Passcode unlock
biometric unlock
downloading VC with VID
wallet binding
qrcode login
Android 10 BLE 5.0 | Passcode unlock | pass
| biometric unlock | pass
| downloading VC with VID | pass
| wallet binding | fail
| qrcode login | pass
Android 11 BLE 5.0 | Passcode unlock | pass
| biometric unlock | pass
| downloading VC with VID | pass
| wallet binding | pass
| qrcode login | fail
Android 11 BLE 4.2 | Passcode unlock | pass
| biometric unlock | fail
downloading VC with VID
wallet binding
qrcode login

## Sheet3 (hidden)
Requestor | Sender
Android 9 BLE 4.2 | Android 10 BLE 4.2
Android 9 BLE 4.2 | Android 10 BLE 5.0
Android 10 BLE 4.2 | Android 11 BLE 5.0
Android 10 BLE 4.2 | Android 10 BLE 5.0
Android 10 BLE 4.2 | Android 12 BLE 5.0
Android 10 BLE 5.0 | Android 10 BLE 5.0
Android 10 BLE 5.0 | Android 11 BLE 5.0 | device name
Android 10 BLE 5.0 | Android 12 BLE 5.0 | redmi 6A | Android 9 BLE 4.2
|  | redmi 7A | Android 10 BLE 4.2
|  | redmi note 10 lite | Android 10 BLE 5.0
|  | redmi note 10 lite, samsung galaxy A03 core | Android 10 BLE 5.0
|  | samsung galaxy A03 core, redmi note 10 lite | Android 11 BLE 4.2
|  | redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0
|  | redmi K20 pro, redmi note 10 lite | Android 11 BLE 5.0
|  | redmi note 10 lite, Vivo Y73 | Android 10 BLE 5.0
|  | Redmi 7A, Redmi 6A | Android 10 BLE 4.2
|  | redmi note 10 lite, redmi 7A | Android 10 BLE 4.2
Android 12 BLE 5.0 | iPhone 15 BLE 5.0 | redmi note 10 lite, redmi 6A | Android 10 BLE 5.0
|  | redmi K20 pro, Redmi 7A | Android 11 BLE 5.0
|  | Vivo Y73, Redmi 7A | Android 12 BLE 5.0
|  | Vivo Y73, Redmi Note 10 lite | Android 12 BLE 5.0
|  | Redmi K20 pro, Redmi note 10 lite | Android 11 BLE 5.0
|  | Redmi note 10 lite, redmi K20 pro | Android 10 BLE 5.0